## WATER TANK VEREENIGING
BILLS OF QUANTITIES FOR THE SUPPLY, DELIVERY AND INSTALLATION OF TWO 305 KILOLITERS AT SEDIBENG TVET COLLEGE, VEREENIGING CAMPUS.
DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
SECTION NO. 1 | H1
BILL NO. 1 | H1
PRELIMINARIES | H1
Disclaimer While the ASAQS aims to ensure that its publications represent best practice, the ASAQS does not accept or assume any liability or responsibility for any events or consequences which derive from the use of the Preliminaries Model Bill. Such Model Bill is not exhaustive and is therefore only intended to provide general guidance to those who wish to make use of it. This publication is provided "as is" without warranty of any kind, either expressed or implied including but without limitation to warranties of merchantability, fitness for a particular purpose and non-infringement
BUILDING AGREEMENT AND PRELIMINARIES | H2
The JBCC Principal Building Agreement (Edition 6.2 - May 2018) prepared by the Joint Building Contracts Committee shall be the applicable building agreement, amended as hereinafter described
The JBCC Principal Building Agreement contract data form an integral part of this agreement
The JBCC General Preliminaries (May 2018) published by the Joint Building Contracts Committee for use with the JBCC Principal Building Agreement (Edition 6.2 - May 2018) shall be deemed to be incorporated in these bills of quantities, amended as hereinafter described
The contractor is deemed to have referred to the abovementioned documents for the full intent and meaning of each clause
The clauses in the abovementioned documents are hereinafter referred to by clause number and heading only
Where any item is not relevant to this agreement such item is marked N/A signifying "not applicable"
Where standard clauses or alternatives are not entirely applicable to this agreement such amendments, modifications, corrections or supplements as will apply are given under each relevant clause heading and such amendments, modifications, corrections or supplements shall take precedence notwithstanding anything to the contrary contained in the abovementioned documents
PREAMBLES FOR TRADES | H2
User note | H4
The General Preambles for Trades 2017 published by the Association of South African Quantity Surveyors is designed to support and extend the abbreviated descriptions utilised in these bills of quantities by inter alia referring to SANS construction standards. Where such preambles are not applicable (eg where BS or Euro construction standards are applicable or the design consultants provide other preambles/specifications for insertion), users are to ensure that the abbreviated descriptions when read in conjunction with the Standard System of Measuring Building Work (seventh edition) for works within South Africa or the Standard Method of Measuring Building Work for Africa 2015 (first edition) for works elsewhere in Africa, represent the full description by extending the abbreviated bills of quantities descriptions and/or by inserting appropriate preambles or specifications
Note that the text of the Standard System of Measuring Building Work (seventh edition) and that of the Standard Method of Measuring Building Work for Africa 2015 (first edition) is the same
The latest version of the General Preambles for Trades should be referred to should the General Preambles for Trades 2017 be revised in future
The General Preambles for Trades 2017 published by the Association of South African Quantity Surveyors shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of items fully described in the said General Preambles will be entertained
Supplementary preambles and/or specifications are incorporated in these bills of quantities to satisfy the requirements of this project. Such supplementary preambles and/or specifications shall take precedence over the provisions of the General Preambles
The contractor's prices for all items throughout these bills of quantities shall take account of and include where applicable for all of the obligations, requirements and specifications given in the General Preambles and in any supplementary preambles and/or specifications
STRUCTURE OF THIS PRELIMINARIES BILL | H2
Section A : A recital of the headings of the individual clauses in the aforementioned JBCC Principal Building Agreement
Section B : A recital of the headings of the individual clauses in the aforementioned JBCC General Preliminaries
Section C : Any special clauses to meet the particular circumstances of the project
PRICING OF PRELIMINARIES | H2
Should the contractor select Option A in the contract data for the adjustment of preliminaries, the amounts entered against the relevant items in these preliminaries are to be divided into one or more of the three categories provided namely fixed (F), value related (V) and time related (T)
SECTION A: PRINCIPAL BUILDING AGREEMENT | H2
Interpretation (A1-A7) | H3
Clause 1.0 - Definitions and interpretation | CONT
Pricing of bills of quantities | CONT
The contractor is to allow opposite each item for all costs in connection therewith. All prices to include, unless otherwise stated, for all materials, fabrication, conveyance and delivery, unloading, storing, unpacking, hoisting, labour, setting, fitting and fixing in position, cutting and waste (except where to be measured in accordance with the standard system of measurement), patterns, models and templates, plant, temporary works, returning of packaging, duties, taxes (other than Value Added Tax), imposts, establishment charges, overheads, profit and all other obligations arising out of this agreement. Value Added Tax (VAT) is to be separately stated on the summary page of these bills of quantities | CONT
Items left unpriced will be deemed to be covered in prices against other items throughout these bills of quantities and no claim for any extras arising out of the contractor's omission to price any item will be entertained | CONT
Prices for all construction equipment, temporary works, services and other items shall include for the supply, maintenance, operating cost and subsequent removal and making good as necessary | CONT
Abbreviated descriptions | CONT
The items in these bills of quantities utilise abbreviated descriptions. It is the intention that the abbreviated descriptions be fully described when read with the applicable measuring system and the relevant preambles and/or specifications. However, should the full intent and meaning of any description not be clear, the contractor shall, before submission of his tender, call for a written directive from the principal agent, failing which it shall be assumed that the contractor has allowed in his pricing for materials and workmanship in terms of international best practice | CONT
Legal status of contractor | CONT
If the contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons then: | CONT
1. These persons are deemed to be jointly and severally liable to the employer for the performance of this agreement | CONT
2. These persons shall notify the employer of their leader who has assigned authority to bind the contractor and each of these persons | CONT
3. The contractor shall not alter its composition or legal status without the prior written consent of the employer | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 2.0 - Law, regulations and notices | CONT
Clause 3.0 - Offer and acceptance F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 4.0 - Cession and assignment F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 5.0 - Documents | CONT
Value Added Tax | CONT
Provision is made in the summary page of these bills of quantities for the inclusion of Value Added Tax (VAT) | CONT
Priced document as specification Clause 5.4 is deemed to be deleted | CONT
The principal agent shall decide which portion of the priced document may be used as a specification of materials and goods or methods, if any | CONT
User note
Electronic issue of drawings All drawings for this project will be issued electronically and the contractor shall be deemed to have received such drawings on the date that such drawings have been dispatched electronically [5.6] | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 6.0 - Employer's agents | CONT
Delegated authority may be dealt with in B 5.0 of the contract data. Insert in the contract data "Refer to Bill No. 1 (Preliminaries)" should it be dealt with in Bill No. 1 | CONT
Delegated authority | CONT
The authority of the principal agent to issue contract instructions [17.1] and perform duties for specific aspects of the works is delegated to agents as follows [6.2]. This does not preclude the principal agent from issuing such contract instructions: | CONT
Add delegated authority as may be required for other relevant consultants not listed hereinafter | CONT
1. Architect | CONT
Note that the contract instructions hereinafter are selected from those listed in clause 17.1 of the JBCC PBA | CONT
1.1 Duties [6.2] : The architect is responsible for the architectural design, functional design and quality inspection of the works | CONT
1.2 Contract instructions [6.2; 17.1] : | CONT
1.2.1 Rectification of discrepancies, errors in description or quantity or omission of items in the agreement other than in the JBCC Principal Building Agreement | CONT
1.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | CONT
1.2.3 The site [13.0] | CONT
1.2.4 Compliance with the law, regulations and bylaws [2.1] | CONT
1.2.5 Provision and testing of samples of materials and goods and/or of finishes and assemblies of elements of the works | CONT
1.2.6 Opening up of work for inspection, removal or re-execution [23.2.4; 26.4.2] | CONT
1.2.7 Removal or re-execution of work | CONT
1.2.8 Removal or substitution of any materials and goods | CONT
1.2.9 Protection of the works | CONT
1.2.10 Making good physical loss and repairing damage to the works [23.2.2] | CONT
1.2.11 Rectification of defects [21.2] | CONT
1.2.12 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion, a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | CONT
1.2.13 Expenditure of budgetary allowances, prime cost amounts and provisional sums | CONT
1.2.14 Appointment of a subcontractor [14.0; 15.0] | CONT
1.2.15 Work by direct contractors [16.0] | CONT
1.2.16 On suspension or termination, protection of the works, removal of construction equipment and surplus materials and goods [29.0] | CONT
2. Quantity surveyor | CONT
2.1 Duties [6.2] : The quantity surveyor is responsible for all measurements, valuations, financial assessments and all other quantity surveying and cost control functions of the works | CONT
2.2 Contract instructions [6.2; 17.1] : | CONT
2.2.1 No contract instructions delegated to the quantity surveyor | CONT
3. Civil and structural engineer | CONT
Note that the contract instructions hereinafter are selected from those listed in clause 17.1 of the JBCC PBA | CONT
3.1 Duties [6.2] : The civil and structural engineer is responsible for all aspects of civil and structural engineering design and quality inspection of the works | CONT
3.2 Contract instructions [6.2; 17.1] : | CONT
3.2.1 Rectification of discrepancies, errors in description or quantity or omission of items in the agreement other than in the JBCC Principal Building Agreement | CONT
3.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | CONT
3.2.3 The site [13.0] | CONT
3.2.4 Compliance with the law, regulations and bylaws [2.1] | CONT
3.2.5 Provision and testing of samples of materials and goods and/or of finishes and assemblies of elements of the works | CONT
3.2.6 Opening up of work for inspection, removal or re-execution [23.2.4; 26.4.2] | CONT
3.2.7 Removal or re-execution of work | CONT
3.2.8 Removal or substitution of any materials and goods | CONT
3.2.9 Protection of the works | CONT
3.2.10 Making good physical loss and repairing damage to the works [23.2.2] | CONT
3.2.11 Rectification of defects [21.2] | CONT
3.2.12 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion, a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | CONT
3.2.13 Expenditure of budgetary allowances, prime cost amounts and provisional sums | CONT
4. Mechanical engineer | CONT
Note that the contract instructions hereinafter are selected from those listed in clause 17.1 of the JBCC PBA | CONT
4.1 Duties [6.2] : The mechanical engineer is responsible for all aspects of mechanical engineering design and quality inspection of the works and, where appointed by the employer for quantity surveying services in respect of the mechanical installations, for all measurements, valuations, financial assessments and all other quantity surveying and cost control functions | CONT
4.2 Contract instructions [6.2; 17.1] : | CONT
4.2.1 Rectification of discrepancies, errors in description or quantity or omission of items in the agreement other than in the JBCC Principal Building Agreement | CONT
4.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | CONT
4.2.3 Compliance with the law, regulations and bylaws [2.1] | CONT
4.2.4 Provision and testing of samples of materials and goods and/or of finishes and assemblies of elements of the works | CONT
4.2.5 Opening up of work for inspection, removal or re-execution [23.2.4; 26.4.2] | CONT
4.2.6 Removal or re-execution of work | CONT
4.2.7 Removal or substitution of any materials and goods | CONT
4.2.8 Protection of the works | CONT
4.2.9 Making good physical loss and repairing damage to the works [23.2.2] | CONT
4.2.10 Rectification of defects [21.2] | CONT
4.2.11 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion, a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | CONT
4.2.12 Expenditure of budgetary allowances, prime cost amounts and provisional sums | CONT
WET SERVICES | H4
SUPERVISOR
Tenderer to allow for a full time working supervisor during the duration of the contract, who shall have the delegated authority to receive instructions and make decisions regarding the contract. | Item | 1 |  | 0
SITE ESTABLISHMENT
Tenderers to allow for all costs which may be required in order to place the necessary facilities on site for safe storage and orderly management purposes for the duration of the contract. | Item | 1 |  | 0
REMOVAL OF WASTE
Tenderer to allow for all costs associated with cleaning the site of all rubbish and waste caused by this contract. | Item | 1 |  | 0
HEALTH AND SAFETY
Allow for Health, Safety and Environmental in accordance with the Specification. | Item | 1 |  | 0
GENERAL ITEMS
Any additional, items that the Tenderer deems necessary for the successful and total completion of the portion of the work required for this Bill. Specify:
Out of town allowance, accommodation & travelling | Item | 1 |  | 0
SEWER | H4
JOINT TRADES
Tenderers to allow for all costs which may be required in order to co-ordinate and liaise with the other Trade Contractors, especially with the electrical contractor. | Item | 1 |  | 0
SUPERVISOR
Tenderer to allow for a full time working supervisor during the duration of the contract, who shall have the delegated authority to receive instructions and make decisions regarding the contract. | Item | 1 |  | 0
SITE ESTABLISHMENT
Tenderers to allow for all costs which may be required in order to place the necessary facilities on site for safe storage and orderly management purposes for the duration of the contract. | Item | 1 |  | 0
REMOVAL OF WASTE
Tenderer to allow for all costs associated with cleaning the site of all rubbish and waste caused by this contract. | Item | 1 |  | 0
HEALTH AND SAFETY
Allow for Health, Safety and Environmental in accordance with the Specification. | Item | 1 |  | 0
ELECTRICAL ENGINEER | CONT
Note that the contract instructions hereinafter are selected from those listed in clause 17.1 of the JBCC PBA | CONT
5.1 Duties [6.2] : The electrical engineer is responsible for all aspects of electrical engineering design and quality inspection of the works and, where appointed by the employer for quantity surveying services in respect of the electrical installations, for all measurements, valuations, financial assessments and all other quantity surveying and cost control functions | CONT
5.2 Contract instructions [6.2; 17.1] : | CONT
5.2.1 Rectification of discrepancies, errors in description or quantity or omission of items in the agreement other than in the JBCC Principal Building Agreement | CONT
5.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | CONT
5.2.3 Compliance with the law, regulations and bylaws [2.1] | CONT
5.2.4 Provision and testing of samples of materials and goods and/or of finishes and assemblies of elements of the works | CONT
5.2.5 Opening up of work for inspection, removal or re-execution [23.2.4; 26.4.2] | CONT
5.2.6 Removal or re-execution of work | CONT
5.2.7 Removal or substitution of any materials and goods | CONT
5.2.8 Protection of the works | CONT
5.2.9 Making good physical loss and repairing damage to the works [23.2.2] | CONT
5.2.10 Rectification of defects [21.2] | CONT
5.2.11 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion, a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | CONT
5.2.12 Expenditure of budgetary allowances, prime cost amounts and provisional sums | CONT
NOTE : The Contractor must not use the Quantities indicated in the Bill to order. These Quantities are merely a guide in order to determine a Contract Value.
Setting out of works | Sum | 1 |  | 0
Provide "as built" drawings | Sum | 1 |  | 0
Additional items that the tenderer wishes to detail in order to complete the contract in good order. No claim will be considered should the tenderer not list such items below. | Sum | 1 |  | 0
7. Fire consultant | CONT
Note that the contract instructions hereinafter are selected from those listed in clause 17.1 of the JBCC PBA | CONT
7.1 Duties [6.2] : The fire consultant is responsible for all aspects of rational fire design and quality inspection of the works | CONT
7.2 Contract instructions [6.2; 17.1] : | CONT
7.2.1 Rectification of discrepancies, errors in description or quantity or omission of items in the agreement other than in the JBCC Principal Building Agreement | CONT
7.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | CONT
7.2.3 Compliance with the law, regulations and bylaws [2.1] | CONT
7.2.4 Provision and testing of samples of materials and goods and/or of finishes and assemblies of elements of the works | CONT
7.2.5 Opening up of work for inspection, removal or re-execution [23.2.4; 26.4.2] | CONT
7.2.6 Removal or re-execution of work | CONT
7.2.7 Removal or substitution of any materials and goods | CONT
7.2.8 Protection of the works | CONT
7.2.9 Making good physical loss and repairing damage to the works [23.2.2] | CONT
7.2.10 Rectification of defects [21.2] | CONT
7.2.11 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion, a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | CONT
7.2.12 Expenditure of budgetary allowances, prime cost amounts and provisional sums | CONT
SUPERVISOR
Tenderer to allow for a full time working supervisor during the duration of the contract, who shall have the delegated authority to receive instructions and make decisions regarding the contract. | Item | 1 |  | 0
SITE ESTABLISHMENT
Tenderers to allow for all costs which may be required in order to place the necessary facilities on site for safe storage and orderly management purposes for the duration of the contract. | Item | 1 |  | 0
REMOVAL OF WASTE
Tenderer to allow for all costs associated with cleaning the site of all rubbish and waste caused by this contract. | Item | 1 |  | 0
HEALTH AND SAFETY
Allow for Health, Safety and Environmental in accordance with the Specification. | Item | 1 |  | 0
GENERAL ITEMS
Any additional, items that the Tenderer deems necessary for the successful and total completion of the portion of the work required for this Bill. Specify:
Out of town allowance, accommodation & travelling | Item | 1 |  | 0
8. Health and safety consultant | CONT
8.1 Duties [6.2] : The health and safety consultant is responsible for all aspects of health and safety of the works. Without derogating from the generality thereof, the health and safety consultant will perform the following specific functions and duties in respect of the health and safety aspects of the works. He shall: | CONT
8.1.1 Act as the employer's agent in terms of the Construction Regulations issued in terms of the Occupational Health and Safety Act,1993 as amended | CONT
8.1.2 Prepare and update the health and safety specification for the works | CONT
8.1.3 Agree with the contractor the health and safety plan for the works | CONT
8.1.4 Carry out regular audits to ensure adherence to the safety plan and compliance with the act and regulations | CONT
8.1.5 Stop the execution of the works where the agreed specification or plan is not adhered to | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 7.0 - Design responsibility F:............................. V:............................ T:............................ | Item | 1 |  | 0
HEALTH AND SAFETY REQUIREMENTS
Occupational Health and Safety Act 85 of 1993 , other applicable legislation including the Construction Regulations, 2014
Prepare and Compile Health and Safety plan as per Site Health and Safety Specifications | Once off | 1 |  | 0
Allow for the preparation of site specific health and safety file including notifying the authorities of the Construction Project | Once off | 1 |  | 0
Personal protective clothing and equipment (PPE) | Item | 1 |  | 0
Health and Safety training | No | 3 |  | 0
Pre-employment, annual and exit medical examination of fitness | Item | 1 |  | 0
Signage, information display and barricading netting for excavations and laydown areas | Item | 1 |  | 0
First aid boxes | Once off | 1 |  | 0
Provision of a full time safety officer (Fully registered with SACPCMP as a CHSO). Allow an amount per month for the duration of the project proposed by the contract. | Per month |  |  | 0
Fencing and securing of the construction site with a solid diamond mesh fence (with green shade netting over it) to prevent unauthorised entrance | Once off | 1 |  | 0
Wheely bins for waste and disposal for hazardous biological waste | Once off | 2 |  | 0
Fire Extinguishers | Once off | 2 |  | 0
PPE (Gloves, Gogles, Earplugs, dust mask) | Daily |  |  | 0
COMMUNITY LIAISON OFFICER (CLO)
Make a provision for an allowance Nine Thousand Rands (R 9000.00) of the CLO per month for the duration of the project proposed by the contractor. | Per month |  |  | 0
Insurances and securities (A8-A11)
Clause 8.0 - Works risk F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 9.0 - Indemnities F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 10.0 - Insurances F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 11.0 - Securities | CONT
Guarantee for payment | CONT
The employer shall provide to the contractor a guarantee for payment in the amount of .......................................................Rand (R...........................) [11.5.1]. The contractor shall consequently waive his lien or right of continuing possession of the works [11.10] | CONT
Extension of waiver of lien | CONT
The contractor shall ensure that a waiver of lien is included in all subcontracts and that the works executed on the site are kept free of all liens and other encumbrances at all times [11.10] | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Execution (A12 - A17)
Clause 12.0 - Obligations of the parties | CONT
Office accommodation The contractor shall provide, maintain and remove on practical completion air conditioned office accommodation with suitable tables and chairs for meetings to be held on the site. Such offices shall be kept clean and fit for use at all times [12.2.18] | CONT
Notice board The contractor shall erect in a position approved by the principal agent, maintain and remove on practical completion a notice board recommended by the South African Institute of Architects and as approved by the principal agent listing the names and logos of the employer, the contractor and the professional consultants. No subcontractor or supplier notice boards may be erected unless permission is granted by the principal agent for such notice boards to be erected [12.2.18] | CONT
Statutory and other notices | CONT
The contractor shall submit and/or comply with all statutory and other notices that may be required by any local or other authority in order not to cause any delay to the commencement of the works by the contractor. The contractor shall pay all deposits or fees in this regard | CONT
It is, however, specifically recorded that the employer shall be responsible for the timeous approval of building plans by any local or other authorities and the payment of any fees or charges related thereto | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 13.0 - Setting out F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 14.0 - Nominated subcontractors | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 15.0 - Selected subcontractors | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 16.0 - Direct contractors Attendance on direct contractors In respect of direct contractors the contractor shall: | CONT
1. Designate an area for the direct contractor to establish a temporary office and workshop and storage of equipment and materials | CONT
2. Allow the use of personnel welfare facilities, where provided | CONT
3. Provide water, lighting and single phase electric power to a position within 50m of the place where the direct contract work is to be carried out, other than fuel or power for commissioning of any installation | CONT
4. Permit the direct contractor to use erected scaffolding, hoisting facilities, etc provided by the contractor, in common with others having the like right, while it remains erected on the site [16.1] | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 17.0 - Contract instructions Site instructions Instructions issued on site are to be recorded in a site instruction book which is to be supplied and maintained on site by the contractor | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Completion (A18 - A24)
Clause 18.0 - Interim completion | N/A | 1 |  | 0
Clause 19.0 - Practical completion F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 20.0 - Completion in sections | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 21.0 - Defects liability period and final completion | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 22.0 - Latent defects liability period F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 23.0 - Revision of the date for practical completion Substitution of materials and goods The removal or substitution of any materials and goods which do not conform to the specification or the contract drawings shall not constitute grounds for the extension of the construction period nor for the adjustment of the contract value [17.1.8; 23.1 & 2] | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 24.0 - Penalty for late or non-completion F:............................. V:............................ T:............................ | Item | 1 |  | 0
Payment (A25 - A27)
Clause 25.0 - Payment | CONT
Prices submitted Where prices are submitted by the contractor or subcontractor during the progress of the works in respect of contract instructions or in regard to a claim under the terms of this agreement and notwithstanding the fact that such prices may be used in an interim payment certificate, there is to be no presumption of acceptance. Should the principal agent wish to accept any such prices prior to the issue of the certificate of final completion, it shall be in writing | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 26.0 - Adjustment of the contract value and final account | CONT
Tenant installation/user requirements delayed There is a possibility that certain works related to tenant installation/user requirements may have to be delayed and may consequently not be executed prior to practical completion | CONT
Should the contractor be instructed to do so he shall execute this work under the conditions pertaining to this agreement on the basis that a separate amount for preliminaries appurtenant to this work (if applicable) is agreed to between the contractor and the principal agent and on condition that instruction to proceed with such work is given to him within a period of three (3) calendar months after the date of practical completion of the works | CONT
The employer reserves the right to omit such work without compensation to the contractor for loss of profit or any other loss which the contractor may suffer as a result of such omission | CONT
Cost of claims All costs incurred by the contractor in the preparation of claims shall be borne by the contractor. This provision shall not preclude an adjudicator or an arbitrator appointed in terms of this agreement [30.6 & 7] from making a determination on costs | CONT
Claims from subcontractors The contractor shall review, assess and adjudicate any claims received by him from any subcontractor and thereafter submit same to the principal agent with a recommendation in order to assist the principal agent in adjudicating the claim [26.6] | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 27.0 - Recovery of expense and/or loss F:............................. V:............................ T:............................ | Item | 1 |  | 0
Suspension and termination (A28 - A29)
Clause 28.0 - Suspension by the contractor | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 29.0 - Termination | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Dispute resolution (A30)
Clause 30.0 - Dispute resolution F:............................. V:............................ T:............................ | Item | 1 |  | 0
Agreement | CONT
The required information of the parties and the amount of the contract sum shall be inserted in the agreement for signature of the agreement by the parties F:............................. V:............................ T:............................ | Item | 1 |  | 0
Contract data | CONT
Tenderer's selections | CONT
Before submission of his tender the contractor is to complete the tenderer's selections in the contract data | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
SECTION B: GENERAL PRELIMINARIES
Should it be necessary to expand on any of the General Preliminaries clauses, the user should list the appropriate General Preliminary clause number and heading and insert the relevant provision under a suitable heading in bold as may be necessary | Item | 1 |  | 0
Definitions and interpretation (B1)
Clause 1.1 - Definitions F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 1.2 - Interpretation F:............................. V:............................ T:............................ | Item | 1 |  | 0
Documents (B2)
Clause 2.1 - Checking of documents F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 2.2 - Provisional bills of quantities | CONT
Multiple procurement These bills of quantities are in multiple procurement format ie the "wet trades" - earthworks, concrete, formwork and reinforcement, precast concrete, masonry, waterproofing and sub-surface drainage - are provisionally (fully) measured and the subsequent trades are budgetary allowances and/or provisional sums F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 2.3 - Availability of construction information | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 2.4 - Ordering of materials and goods F:............................. V:............................ T:............................ | Item | 1 |  | 0
Previous work and adjoining properties (B3)
Clause 3.1 - Previous work - dimensional accuracy F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 3.2 - Previous work - defects F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 3.3 - Inspection of adjoining properties F:............................. V:............................ T:............................ | Item | 1 |  | 0
The site (B4)
Clause 4.1 - Handover of site in stages F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 4.2 - Enclosure of the works | Item | 1 |  | 0
Hoarding requirements, other than already described in clause 4.2, in the contract data or drawings
F:............................. V:............................ T:............................ | CONT
Clause 4.3 - Geotechnical and other investigations F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 4.4 - Encroachments F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 4.5 - Existing premises occupied F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 4.6 - Services - known F:............................. V:............................ T:............................ | Item | 1 |  | 0
Management of contract (B5)
Clause 5.1 - Management of the works F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 5.2 - Progress meetings F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 5.3 - Technical meetings F:............................. V:............................ T:............................ | Item | 1 |  | 0
Samples, shop drawings and manufacturer's instructions (B6)
Clause 6.1 - Samples of materials F:............................. V:............................ T:........................... | Item | 1 |  | 0
Clause 6.2 - Workmanship samples F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 6.3 - Shop drawings F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 6.4 - Compliance with manufacturer's instructions F:............................. V:............................ T:............................ | Item | 1 |  | 0
Deposits and fees (B7)
Clause 7.1 - Deposits and fees F:.......................... V:........................... T:......................... | Item | 1 |  | 0
Temporary services (B8)
Clause 8.1 - Water F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 8.2 - Electricity F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 8.3 - Ablution and welfare facilities F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 8.4 - Communication facilities F:............................. V:............................ T:............................ | Item | 1 |  | 0
Prime cost amounts (B9)
Clause 9.1 - Responsibility for prime cost amounts | CONT
Where details of materials for which prime cost amounts are to be allowed are readily available, the quantity surveyor may elect to insert the relevant prime cost amounts in measured items, which measured items shall contain sufficient detail for the contractor to price for fixing and installation, waste, etc F:............................. V:............................ T:............................ | Item | 1 |  | 0
Attendance on subcontractors (B10)
Clause 10.1 - General attendance F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 10.2 - Special attendance | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
General (B11)
Clause 11.1 - Protection of the works F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 11.2 - Protection/isolation of existing works and works occupied in sections F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 11.3 - Security of the works F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 11.4 - Notice before covering work F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 11.5 - Disturbance | CONT
The following clause may be used should "disturbance" [11.5] need to be extended | CONT
Disturbance All work is to be carried out in such a manner as to cause no unacceptable or unreasonable dust, noise, vibrations, nuisance, inconvenience, annoyance and the like to the public, others, other properties and traffic in so far as they exceed the permissible limitations set by government legislation or by the local authority. Any delays, stoppages and the like arising from or in order to comply with the above will not constitute grounds for an adjustment to the construction period or contract value whatsoeverF:........................ V:.........................T:......................... | Item | 1 |  | 0
Clause 11.6 - Environmental disturbance | CONT
Controlling all forms of pollution The contractor shall be responsible for and take all precautions in controlling by whatever means necessary all forms of pollution emanating from the site during the construction period due inter alia to noise, artificial light, wind-blown sand, dust, deposits of mud, etc | CONT
The contractor is to ensure that all roads which border the site and are used by the contractor during the execution of the works are kept clean and free of any dirt or debris caused by the execution of the works | CONT
Environmental management plan The employer has prepared an environmental management plan (EMP). The contractor shall price opposite this item for compliance with all the requirements of such EMP F:........................ V:.........................T:......................... | Item | 1 |  | 0
Clause 11.7 - Works cleaning and clearing F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 11.8 - Vermin F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 11.9 - Overhand work F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 11.10 - Tenant installations F:............................. V:............................ T:............................ | Item | 1 |  | 0
Clause 11.11 - Advertising F:............................. V:............................ T:............................ | Item | 1 |  | 0
SECTION C: SPECIFIC PRELIMINARIES
Warranties for materials and workmanship Where warranties for materials and/or workmanship are called for, the contractor shall obtain a written warranty, addressed to the employer, from the entity supplying the materials and/or executing the work and shall deliver same to the principal agent on final completion of the contract | CONT
The warranty shall state that workmanship, materials and installation are warranted for a specific period from the date of practical completion and that any defects that may arise during the specified period shall be made good at the expense of the entity supplying the materials and/or doing the work, upon written notice to do so | CONT
The warranty will not be enforced if the work is damaged by defects in the execution of the works, in which case the responsibility for replacement shall rest entirely with the contractor F:............................. V:............................ T:............................ | Item | 1 |  | 0
Overtime Should overtime be required to be worked for any reason whatsoever, the cost of such overtime is to be borne by the contractor unless the principal agent has specifically authorised, prior to execution thereof, that costs for such overtime are to be borne by the employer F:........................ V:.........................T:......................... | Item | 1 |  | 0
Cooperation of the contractor for cost management It is specifically agreed that the contractor accepts the obligation of assisting the principal agent in implementing proper cost management. The contractor will be advised by the principal agent of all cost management procedures which will be implemented to ensure that the contract value does not exceed the budget F:........................ V:.........................T:......................... | Item | 1 |  | 0
Overloading The contractor shall take all necessary steps to ensure that no damage occurs due to overloading of any portion of the works or temporary works eg scaffolding, etc. The contractor shall submit details of his proposed loading, storage, plant erection, etc to the principal agent for approval prior to proceeding with such loading, storing or erecting and shall comply with and pay for the principal agent's requirements in connection with the provision of temporary support work, etc. Any damage caused to the works by overloading shall be made good by the contractor at his sole expense F:........................ V:.........................T:......................... | Item | 1 |  | 0
Propping of floors below The contractor is advised that propping of floors below may be required if he wishes to use any areas of completed suspended reinforced concrete slabs for vehicle access, storage of materials and goods and location of plant, scaffolding, etc. The location of these areas and any necessary propping shall be approved by the principal agent and the cost thereof shall be borne by the contractor F:........................ V:.........................T:......................... | Item | 1 |  | 0
Testing of flat roof waterproofing for watertightness Flat roof waterproof areas shall be flooded and kept "ponded" for at least forty eight (48) hours as a test to ensure the watertightness of the waterproofing and before any further construction work is carried out above the waterproofing F:........................ V:.........................T:......................... | Item | 1 |  | 0
Health and safety | CONT
Without limiting the generality of the provisions of clause 2.0, the contractor's attention is drawn to the provisions of the Construction Regulations issued in terms of the Occupational Health and Safety Act, 1993 as amended. It is specifically stated that the employer shall prepare a documented health and safety specification for the works and that the employer shall ensure that the contractor has made provision for the cost of health and safety measures during the execution of the works. The contractor shall price opposite this item for compliance with the act and the regulations and the reasonable provisions of the aforementioned health and safety specification [2.1] | CONT
Health and safety Without limiting the generality of the provisions of clause 2.0, the contractor's attention is drawn to the provisions of the Construction Regulations issued in terms of the Occupational Health and Safety Act, 1993 as amended. It is specifically stated that the employer shall prepare a documented health and safety specification for the works and that the employer shall ensure that the contractor has made provision for the cost of health and safety measures during the execution of the works. The contractor shall price opposite this item for compliance with the act and the regulations and the provisions of the aforementioned health and safety specification [2.1] | CONT
The contractor shall: 1. Comply with the health and safety specification for the works 2. Prepare and agree with the health and safety consultant the health and safety plan for the works 3. Cooperate with the health and safety consultant in all respects 4. Manage the compliance of all subcontractors with the regulations and with the health and safety plan and specification 5. Conform to the conditions contained in the employer's health and safety specification | CONT
F:............................. V:............................ T:............................ | Item | 1 |  | 0
Green star building certification F:........................ V:.........................T:......................... | Item | 1 |  | 0
Broad based black economic empowerment (BBBEE) Tenders submitted will be evaluated taking into account their empowerment rating The employer will be monitoring the broad based black economic empowerment (BBBEE) status of the contractor throughout the execution of the works | CONT
The contractor is to submit to the principal agent on an annual basis a schedule of spend, split into vendors engaged as subcontractors and suppliers indicating their BBBEE rating including proof of the said rating F:........................ V:.........................T:......................... | Item | 1 |  | 0
Advertising rights The employer may elect to contract with advertising agencies for the erection of advertising hoardings, banners, wraps or the like for the duration of the contract. The contractor shall not prevent such an arrangement and will assist in the facilitation of same. The position and type of advertising structure to be agreed with the principal agent so as not to hinder the contractor in meeting his obligations under this agreement F:........................ V:.........................T:......................... | Item | 1 |  | 0
Confidentiality The contractor undertakes to maintain in confidence any and all information regarding this project and shall obtain appropriate similar undertakings from all subcontractors and suppliers. Such information shall not be used in any way except in connection with the execution of the works No information regarding this project shall be published or disclosed without the prior written consent of the employer F:........................ V:.........................T:......................... | Item | 1 |  | 0
Media releases All rights of publication of articles in the media, together with any advertising relating thereto or in any way connected with this project, shall vest with the employer The contractor together with his subcontractors shall not, without the prior written consent of the employer, cause any statement or advertisement connected with this project to be printed, screened or aired by the media F:........................ V:.........................T:......................... | Item | 1 |  | 0
SUMMARY OF CATEGORIES
Category : Fixed R........................................ Category : Value R........................................ Category : Time R........................................ | Item | 1 |  | 0
TOTAL- SECTION 1- BILL NO.1 - PRELIMINARIES AND GENERAL |  |  |  | 0
SECTION 2: STEEL WATER TANK
SECTION NO. 2
BILL NO.1 | H1
EARTHWORKS (PROVISIONAL) | H1
PREAMBLES | H2
The tenderer referred to the relevent Clauses in the separate
document Model Preambles for Trades and to the
Supplementary Preambles
SUPPLEMENTARY PREAMBLES | H2
Nature of ground | H3
A soils invistigation has been carried out on site by the engineer
and the report is annexed to these bills of quantities.
Descriptions of excavations shall be deemed to include all
ground conditions classifiable as "earth" described in the above
report and where conditions of a more difficult character are
indicated these are separately measured
Carting away of excavated material | H3
Descriptions of carting away of excavated material shall be
deemed to include loading excavated material onto trucks
directly from the excavations or, alternatively from stock piles
situated on the building site
The following in workgroup 104 | H3
ALTERATIONS
General site clearance
SITE CLEARANCE AND REMOVAL OF TREES, ETC. | H2
Clear site and remove all debris, shrubs etc | H3
Clear site of existing shrubs and trees | m2 | 558 |  | 0
Removal of trees not exceeding 3m girth | No | 3 |  | 0
EXCAVATION, FILLING, ETC INCLUDING BULK | H2
Excavation in earth not exceeding 2m deep | H4
Bulk excavations | m3 | 1072 |  | 0
Shallow excavations for biddim cloth, Nextube drainex 110mm x6mm slotted pipe | m3 | 73 |  | 0
Excavation in compacted material not exceeding 2m deep
2500mm x 2500mm x 500mm excavations on earth for underground beams | m3 | 293 |  | 0
Extra over trench and hole excavations in earth for excavation in: | H4
Soft rock | m3 | 107 |  | 0
Hard rock | m3 | 54 |  | 0
Extra over all excavations for carting away of surplus material to a dumbing site which is approximately 10km from the site. The dumbing site is to be located by the contractor. | H4
Surplus material from excavations and/or stock piles on site to | m3 | 1072 |  | 0
a dumping site to be located by the contractor
Risk of collapse of excavations | H4
Sides of bulk excavations not exceeding 1,5m exceeding 1.5m not exceeding 3m deep | m2 | 207 |  | 0
Keeping excavations free of water | H4
Keeping excavations free of all water other than subterranean water | Item | 1 |  | 0
FILLING ETC | H2
Filling of natural gravel material supplied by the contractor, compacted to 98% Mod AASHTO density. | H4
Backfilling to excavated hole, etc with 200mm pioneer layer of 110mm nominal stone size | m3 | 97 |  | 0
150mm imported G5 material compacted to 95% Mod AASSHTO to the extend of paving | m3 | 655 |  | 0
150mm inert G6 material stabilised at 3-4% to C3 and compacted to 97% Mod AASHTO | m3 | 219 |  | 0
200mm insitu G9 material compacted to 83% Mod AASHTO | m3 | 97 |  | 0
Compaction of surfaces | H4
Compaction of ground surface under floors etc including | m2 | 5487 |  | 0
scarifying for a depth of 150mm, breaking down oversize
material, adding suitable material where necessary and
compacting to 93% Mod AASHTO density
SOIL POISONING | H2
Soil insecticide | H4
Under floors etc including forming and poisoning shallow | m2 | 485 |  | 0
furrows against foundation walls etc, filling in furrows and
ramming
To the sides of trenches etc | m2 | 207 |  | 0
TESTS | H2
Prescribed tests to determine degree of compaction or other | H4
properties of ground or filling
"Modified AASHTO Density" test | No | 80 |  | 0
"Natural Califonia Bearing Ratio" test | No | 5 |  | 0
"Field Density "test, including "Optimum Moisture Content" test | No | 5 |  | 0
(four readings per test)
TOTAL - SECTION NO. 2 - BILL NO. 1 - EARTHWORKS |  |  |  | 0
SECTION NO. 2
BILL NO.2 | H1
CONCRETE, FORMWORK AND | H1
REINFORCEMENT
PREAMBLES | H1
The Tenderer is referred to the relevant Clauses in the
seperate document Model Preambles for Trades and to the
Supplementary Preambles
SUPPLEMENTARY PREAMBLES | H2
The costs of making, storing and testing of concrete test cubes
as required under clause 7 "Tests" of SABS 1200 G shall
include the cost of providing cube moulds necessary for the
purpose, for testing costs and for submitting reports on the
tests to the architect. The testing shall be undertaken by an
independent firm or institution nominated by the contractor and
to the approval of the architect. (Test cubes are measured
separately)
Formwork | H3
Description of formwork shall be deemed to include use and
waste only (except where described as "left in" or "permanent"),
for fitting together in the required forms, wedging, plumbing and
fixing to true angles and surfaces as necessary to ensure easy
release during stripping and for reconditioning as necessary
before re-use
The vertical strutting shall be carried down to such construction
as is sufficiently strong to afford the required support without
damage and shall remain in position until the newly constructed
work is able to support itself
Formworks to soffits of solid etc shall be deemed to be slabs
not exceeding 250mm thick unless otherwise described
Formwork to sides of bases, pile caps, ground beams, etc will
only be measured where it is prescribed by the engineer for
design reasons. Formwork necessitated by irregularity or
collapse of excavated faces will not be measured and the cost
thereof shall be deemed to be included in the allowance for
taking the risk of collapse of the sides of the excavations,
provision for which is made in "Earthworks"
REINFORCED CONCRETE CAST AGAINST | H2
EXCAVATED SURFACES
40Mpa/19mm concrete | H4
Underground beams | m3 | 293 |  | 0
Ground floor beams | m3 | 243 |  | 0
Ground floor slab | m3 | 146 |  | 0
15Mpa/19mm concrete | H4
50mm concrete blind | m3 | 25 |  | 0
TEST BLOCKS | H2
Making and testing 150 x 150 x 150mm concrete strength test | No | 25 |  | 0
cube (Provisional)
FORMWORK | H2
Formwork to soffits of solid slabs etc shall be deemed to be to
slabs not exceeding 250mm thick unless otherwise described
NOTE: Unless otherwise stated herein, all items in this bill shall
be deemed to fall into Work Group No 111 for Haylet formula
purposes
NOTE: All formwork utilised on the ground floor for the surface
bed should and can be utilised later on the first and second
floors when pouring the 30 Mpa, 70mm thick concrete topping
ROUGH FORMWORK (DEGREE OF ACCURACY II)
Smooth formwork to | H4
Ground floor slab | m | 70 |  | 0
Ground floor beams | m2 | 1246 |  | 0
REINFORCEMENT | H2
High tensile steel reinforcement to structural concrete work | H4
Y16 | t. | 4 |  | 0
Y12 | t. | 20 |  | 0
TOTAL SECTION NO. 2 BILL NO. 2 - CONCRETE. FORMWORK AND REINFORCEMENT |  |  |  | 0
SECTION NO. 2
BILL NO. 4 | H1
WATERPROOFING | H1
PREAMBLES | H2
Geotextile/Biddim cloth to be approved membrane | m2 | 485 |  | 0
TOTAL SECTION NO. 2 BILL NO. 4 - WATERPROOFING |  |  |  | 0
SECTION NO.2 | H1
BUILDING WORKS | H3
BILL NO.5 | H1
ELEVATED STEEL WATER STORAGE TANK
VEREENIGING CAMPUS
Supply and installation of 305 kilo litres/ 305 000 litres galvanized steel water tank including all special parts, complete as per the Engineer's drawings and instructions. Before pricing refer to drawing no SDCL_CIEG_031_VER_STR_04_00 for the complete details. | Item | 2 |  | 0
Supply and installation of submisable commercial borehole pump SVM70/15, Output power 1.1 Kilowatt, Three phase electrical (AC) conection | Item | 1 |  | 0
TOTAL SECTION NO.2 - BILL NO.5 - ELEVATED STEEL WATER STORAGE TANKS |  |  |  | 0
SECTION NO.2 | H1
BUILDING WORKS | H3
BILL NO.6 | H1
BOREHOLE
Scientific Water Sitting | H4
Scientific Water Sitting to be determined after drilling with a 1 hour yield test. | Item | 1 |  | 0
Drilling of the borehole shall be deemed to include percussion report, gravel pack, perforation and ravelling. | H4
Drilling of borehole | m | 100 |  | 0
Casing of borehole 177 x 2.5mm steel casing | m | 50 |  | 0
1 Hour Yield Test | H4
A 1 hour yield test is to be conducted first to determine if the borehole is delivering enough water for a 24 hour yield test. | Item | 1 |  | 0
24 Hour Yield Test | H4
This yield test shall include site establishment and de-establishment, setting up and installation of test pump. Additionals of the yield test shall include (laying out of discharge hose, step test, recovery monitoring, CD test, geohydrologist). | Item | 1 |  | 0
Water Quality Test
The water quality test must be done at borehole water sample SANAS accredited laboratory. Provide analysis report and purification recommendation. | Item | 1 |  | 0
Water Use Lisence Application (WULA)
Allow an amount for the registration of the borehole. | Item | 1 |  | 0
TOTAL SECTION NO.2 - BILL NO.6 - BOREHOLE |  |  |  | 0
SECTION NO.2 | H1
BUILDING WORKS | H3
BILL NO.7 | H1
ELECTRICAL WORKS
LOW VOLTAGE DISTRIBUTION
Distribution Board
Distribution board shell c/w busbars, neutral bars and earthing | No | 1 |  | 0
Circuit breakers to be Schneider, ABB, CBI or Hager
(a) new 50A CB 2,5KA, Three phase | each | 1 |  | 0
(b) new 20A CB 2,5KA, single phase | each | 1 |  | 0
(c) new 40A CB 2,5KA, Three phase | each | 1 |  | 0
(d) new 20A CB 2,5KA, Three phase | each | 1 |  | 0
(e) Surge Arrester 10kA class triple pole
Low Voltage Cables From Tramsformer to Kiosks
600/1000V grade stranded conductor cables installed on cable trays, in sleeves or trenching. Trenching, sleeves and wire ways are measured elsewhere. Terminations of conductors are also measured elsewhere.
35mm2 PVC/SWA/PVC/PVC 4 Core CU- From main supply to Main DB | meters | 168 |  | 0
10mm2 PVC/SWA/PVC/PVC 3 Core CU- From main BD to the Filtration System | meters | 56 |  | 0
25mm2 PVC/SWA/PVC/PVC 4 Core CU- From Main BD to Borehole | meters | 336 |  | 0
16mm2 PVC/SWA/PVC/PVC 4 Core CU- From Main BD to Pump | meters | 56 |  | 0
Low Voltage Cable Terminations
Cable terminations complete glands, shrouds, lugs, connections and commissioning.
35mm2 PVC/SWA/PVC/PVC 4 Core CU | Each | 8 |  | 0
10mm2 PVC/SWA/PVC/PVC 3 Core CU | Each | 6 |  | 0
25mm2 PVC/SWA/PVC/PVC 4 Core CU | Each | 8 |  | 0
16mm2 PVC/SWA/PVC/PVC 4 Core CU | Each | 8 |  | 0
Bare Stranded Copper Earth Wire
Bare stranded copper earth wire strapped to cables, terminations are measured elsewhere.
25mm2 CU | meters | 168 |  | 0
10mm2 CU | meters | 56 |  | 0
25mm2 CU | meters | 336 |  | 0
16mm2 CU | meters | 56 |  | 0
Cable Trenches
Excavate for cable and sleeve trench including temporary support of sides, keeping excavations dry, backfilling and compacting to the engineers specification including bedding under and filling around cable comprising sifted sand
(a) Soil- New Trenches from main kiosk to main DB and to borehole | m3 | 168 |  | 0
Tarred Surfaces
(a) Saw-cutting asphalt surface not exceeding 200mm thick and 1000mm wide | m2 | 7 |  | 0
(b) Preparation of compaction of construction bed material to 90% Modaashto density 1 metre wide | m2 | 7 |  | 0
(c) Reinstatement of asphalt surfaced roads complete with all associated layerworks1 metre wide | m2 | 7 |  | 0
Paved Surfaces
(a) Remove existing paving bricks 1 metre wide | m2 | 7 |  | 0
(b) Preparation of compaction of construction bed material to 90% Modaashto density | m2 | 7 |  | 0
(c) Take from stockpile and install 60mm precast double zig-zag interlocking type paving , laid on 25mm thick riversand bed vibrated with plate compactor and plastered and broomed into joints on completion | m2 | 3 |  | 0
(d) 60mm precast double zig-zag interlocking type paving , laid on 25mm thick riversand bed vibrated with plate compactor and plastered and broomed into joints on completion | m2 | 3 |  | 0
Precast Kerbs
(a) Remove existing precast concrete kerbs | m | 5 |  | 0
(b) Take from stockpile and install precast concrete kerbs | m | 5 |  | 0
Testing and Commissioning
(a) Testing and commissioning of complete system | Lot | 1 |  | 0
TOTAL- SECTION 2- BILL NO.7 - ELECTRICAL RETICULATION |  |  |  | 0
SECTION NO.2 | H1
BUILDING WORKS | H3
BILL NO.8 | H1
MECHANICAL WORKS
SITE FIRE PROTECTION
PUMPS
Close coupled vertical multistage pump complete with motor, two off isolationg valves, strainer, non-return valve, pipe unions, two pressure gauges, supports, fixing and pipe connections as per the layouts and Technical Specification.
Hydrant Booster - 20l/s @ 600kPa | No | 1 |  | 0
Jockey pump - 1,5l/s @ 400kPa | No | 1 |  | 0
CONTROLS
Control system for hydrant and jockey booster pumps including weatherproof control panel, level switches, pressure switches, control cabling, sensors, sensor wiring, GMS conduit weatherproof as per the Technical Specification.
Controls | Item | 2 |  | 0
DIAPHRAGM TANKS
600 litre | No | 1 |  | 0
450 litre | No | 1 |  | 0
PIPING
uPVC Class 16 pressure pipes with butt welded joints
110mm Pipes laid in and including excavation not exceeding 1m deep | m | 30 |  | 0
65mm Pipes laid in and including excavation not exceeding 1m deep | m | 16 |  | 0
50mm Pipes laid in and including excavation not exceeding 1m deep | m | 22 |  | 0
25mm Pipes laid in and including excavation not exceeding 1m deep | m | 30 |  | 0
Extra over uPVC Class 16 pressure pipes with couple on joints
110mm Fitting | No | 30 |  | 0
65mm Fitting | No | 9 |  | 0
50mm Fitting | No | 11 |  | 0
25mm Fitting | No | 16 |  | 0
Galvanised Mild Steel pressure pipes
110mm Pipes | m | 40 |  | 0
50mm Pipes | m | 30 |  | 0
25mm Pipes | m | 80 |  | 0
Extra over Galvanised Mild Steel pressure pipes
110mm Fitting | No | 24 |  | 0
40mm Fitting | No | 18 |  | 0
25mm Fitting | No | 46 |  | 0
FIRE EQUIPMENT
Supply, delivery, installation, commissioning and testing of the fire protection equipment and signage complete with fixtures, fittings, connections and accessories.
Fire hose reel inside steel cabinate, 30m hose at discharge rate of 0,5l/s @400kPa | No | 4 |  | 0
Fire hydrant with key opening mechanism, discharging at 20l/s @600kPa | No | 4 |  | 0
Assembly point signage on a steel pole | No | 3 |  | 0
Fire Equipment Signage laminated to glow in the dark, size 190 x 190mm | No | 24 |  | 0
Twin booster connection with pressure gauge | No | 1 |  | 0
Make provision for Valve chamber at the boundary fence of the facility as per layout | Item | 1 |  | 0
PAINTING
Painting of the fire protection installation as per the Standard Specifications. | m2 | 30 |  | 0
PRESSURE TESTING
The Contractor shall make provision to pressure test the installation during construction - See Standard specification. | Item | 1 |  | 0
PLUMBING CERTIFICATE (CoC)
The Contractor shall make provision to issue certiicate of compliance (COC) for the entire installation after commissioning - See Standard specification. | Item | 1 |  | 0
TOTAL- SECTION 2- BILL NO.8 - MECHANICAL WORKS |  |  |  | 0
SECTION NO.2 | H1
BUILDING WORKS | H1
BILL NO.9 | H1
EXTERNAL WORKS
EARTHWORKS | H2
For preambles see "Model Preambles for Trades (2017
Edition)" and Supplementary preambles as specified in the
Trades.
---------------------------------------
SUPPLEMENTARY PREAMBLES | H2
Nature of ground | H4
The nature of the ground is assumed to be sandy weathered
granite, therefore "earth", but possibly interspersed with
"hard rock"
Excavation for working space in rock | H4
Notwithstanding clause 11 page 8 of the Standard System
of Measuring Building Work, excavation for working space
in rock will be measured in cubic metres to the extent
executed and given as "extra over" bulk excavation or
trench and hole excavation as the case may be
Carting away of excavated material | H4
Descriptions of carting away of excavated material shall be
deemed to include loading excavated material onto trucks
directly from the excavations or, alternatively, from stock
piles situated on the building site
Filling | H4
Notwithstanding the reference to prescribed multiple
handling in clause 1 page 6 of the Standard System of
Measuring Building Work, prices for filling and backfilling
shall include for all selection and any multiple handling of
material
Soil poisoning | H4
Ant and weed poisoning will be applied in accordance to
SABS specifications by Registered and Approved
Specialists who will issue a five (5) year guarantee. The
contractor will only be paid for this items once they have
produced the said cerfificate to the Project Manager.
"Polycop" polypropylene pipes | H3
Polypropylene pipes 54mm diameter and under shall be
seamless copper coloured class 16 pipes jointed with
"Fast-fuse" heat welded thermoplastic or brass compression
fittings as designed for use with copper pipes as stated
Pipes shall be firmly fixed to walls etc with coloured nylon
snap-in pipe clips with provision for accommodating thermal
movement and jointed and fixed strictly in accordance with the
manufacturer's instructions
All pipe diameters are nominal external
"Polylink" polypropylene pipes: | H3
Polypropylene pipes 63mm diameter and over shall be class 12
pipes jointed with cast iron "Supraclamp" running joints
Fusion welded bends, once or twice mitred as necessary, and
tees shall be factory manufactured
Fusion welded bends and tees shall include jointing to pipes
with PVC rubber ring double Z joint couplers
Branch tees shall include flanged and bolted joints to "Polycop"
branch pipes in addition and for brass compression male iron to
copper straight couplers
Reducers shall include jointing to pipes with PVC rubber ring
double Z joint couplers and reducers shall be of sufficient
overall length to accommodate same
All pipes shall be jointed and fixed strictly in accordance with
the manufacturer's instructions
All pipe diameters are nominal external
uPVC pipes and fittings: | H3
Sewer and drainage pipes and fittings shall be jointed and
sealed with butyl rubber rings
Soil, waste and vent pipes and fittings shall be solvent weld
jointed
uPVC pressure pipes and fittings: | H3
Pipes for water supply shall be of the class stated
Pipes of 40mm diameter and smaller shall be plain ended with
solvent welded uPVC loose sockets and fittings
Pipes of 50mm diameter and greater shall have sockets and
spigots with push in type integral rubber ring joints. Bends shall
be uPVC and all other fittings shall be cast iron, all with similar
push-in type joints
Copper pipes: | H3
Pipes shall be hard drawn and half-hard pipes of the class
stated. Class 0 (thin walled hard drawn) pipes shall not be bent.
Class 1 (thin walled half-hard), class 2 (half-hard) and class 3
(heavy walled half-hard) pipes shall only be bent with benders
with inner and outer formers. Fittings to copper waste, vent and
anti-syphon pipes, capillary solder fittings and compression
fittings shall be "Cobra Watertech" type. Capillary solder fittings
shall comply with ISO 2016. Only compression fittings shall be
used in walls or in ground
Reducing fittings | H3
Where fittings have reducing ends or branches they are
described as "reducing". In the case of pipes with diameters
not exceeding 60mm only the largest end or branch size is
given. Should the contractor wish to use other fittings and
bushes or reducers he may do so on the understanding that no
claim in this regard will be entertained. In the case of pipes
with diameters exceeding 60mm all sizes are given and no
claim for extra bushes, reducers, etc will be entertained
Wire gratings | H3
Descriptions of gutter outlets etc shall be deemed to include
wire balloon gratings
Exposed concrete surfaces | H3
Exposed surfaces of concrete stormwater channels, cover
slabs, inspection eye marker slabs, gulley tops, cleaning eye
tops, catchpits, inspection chambers, etc shall be finished
smooth with plaster
Excavations | H3
No claim for rock excavation will be entertained unless the
contractor has timeously notified the quantity surveyor thereof
prior to backfilling
"Soft rock" and "hard rock" shall be as defined in "Earthworks"
Laying, backfilling, bedding, etc. of pipes | H3
Pipes shall be laid and bedded and trenches shall be carefully
backfilled in accordance with manufacturers' instructions
Where no manufacturers' instructions exist pipes shall be laid in
accordance with clauses 5.1 and 5.2 of each of the following:
SABS 1200 L : Medium-pressure pipelines
LD : Sewers
LE : Stormwater drainage
Pipe trenches etc shall be backfilled in accordance with clauses
3, 5.5, 5.6, 5.7 and 7 of SABS 1200
DB : Earthworks (Pipe trenches)
Pipes shall be bedded in accordance with clauses 3.1 to 3.4.1,
5.1 to 5.3 and 7 of SABS 1200
LB : Bedding (Pipes).
Unless otherwise described bedding of rigid pipes shall be
class B bedding
Flush pans | H3
Flush pans shall have straight or side outlets and "P" or "S"
traps as necessary
Stainless steel basins, sinks, wash troughs, urinals, etc. | H3
Units shall have standard aprons on all exposed edges and
tiling keys against walls where applicable
Waste unions | H3
Descriptions of waste unions shall be deemed to include rubber
or vulcanite plugs and chains fixed to fittings
Steel sectional water tanks | H3
Tanks shall comply with SABS CKS 114
"Densyl" petrolatum anti-corrosion tape | H3
Pipes to be taped shall be coated with the appropriate primer
and the tape shall be applied with minimum 15mm lap per
spiral unless otherwise described
Couplings and fittings to pipes shall be taped in strict
accordance with the manufacturer's instructions including all
mastic, tape, "Layflat" sheeting, securing of same, etc
Prices for wrapping of pipes shall include for all work as
described to couplings in the length
ROADWORKS AND PAVING
Alterations | H2
Carefully, conduct removal of 35mm asphalt as per engineer's instruction | m2 | 224 |  | 0
Carefully conduct removal of 80mm pavement as per engineer's instruction | m2 | 189 |  | 0
Carefully conduct removal of concrete kerbs as per engineer's instruction | m | 72 |  | 0
Asphalt replacement | H2
Install a new 35mm asphalt, installation complete with all items as per the instruction of the engineer | m2 | 224 |  | 0
Reuse 80mm pavemnet blocks, installation complete with all items as per the instruction of the engineer | m2 | 189 |  | 0
Reinstall the removed concrete kerbs, installation complete with all items as per engineer's instruction | m | 72 |  | 0
Site clearance | H3
Digging up and removing rubbish, debris, vegetation, | m2 | 494 |  | 0
hedges, shrubs and trees not exceeding 200mm girth, bush,
etc.
BULK EXCAVATION EXCAVATION, FILLING, ETC. | H2
Excavate in all materials and use for embankment or backfill or dispose as required | H4
Excavate to reduced level | m3 | 149 |  | 0
Extra over bulk excavations in earth for excavation | H4
Soft rock | m3 | 14.9 |  | 0
Hard rock | m3 | 7.45 |  | 0
Extra over all excavations for carting away | H4
Surplus material from excavations on site to a dumping site | m3 | 171.35 |  | 0
to be located by the contractor. The salvage yard should not be more 20km from site.
Keeping excavations free of water | H4
Keeping excavations free of all water other than | Item | 1 |  | 0
subterranean water
Compaction of surfaces | H4
Compaction of ground surface under floors etc including | m2 | 223 |  | 0
scarifying for a depth of 150mm, breaking down oversize
material, adding suitable material where necessary and
compacting to 93% Mod AASHTO density
SOIL POISONING | H2
Soil insecticide | H4
To bottoms of bulk excavations | m2 | 494 |  | 0
SUB BASE | H2
Earth filling obtained from the excavations and/or prescribed stock piles on site including haulage approximately 150m from perimeter of excavations or stock piles
Rip and scarify 150mm in situ layer, wet and apply heavy rollers or rammers to achieve 93% MOD AASHTO at OMC (Optimum Moisture Content). Perform testing (DCP) to such prepared ground and further wet and compact until minimum CBR | m2 | 494 |  | 0
Approved filling material supplied by the contractor
Coarse river sand filling supplied by the contractor | m3 | 25 |  | 0
Upper selected layer (G6) compacted to 95% MOD AASHTO, 150mm thick | m3 | 75 |  | 0
Upper selected layer (G5) compacted to 95% MOD AASHTO, 150mm thick | m3 | 149 |  | 0
150mm C4 stabilized layer compacted to 98% MOD ASSHTO density | m3 | 75 |  | 0
KERBING AND CHANNELING | H2
Precast concrete, finished smooth on exposed surfaces including bedding, jointing and pointing
Barrier kerb (Figure 7) with 150 x 150 x 300mm unreinforced concrete haunching at back of each joint including excavation, backfilling, etc | m | 95 |  | 0
60 mm paving blocks, Shape S-A Class 30/2.0 (in accordance with SANS 1058 latest edition) on 20 mm bedding sand (COLTO 7302(a) )
Paving of 60mm thick blocks including edge blocks | m2 | 494 |  | 0
Prescribed density tests on filling | H4
Modified AASHTO Density test | No | 5 |  | 0
Natural California Bearing Ratio test | No | 5 |  | 0
Field Density test, including "Optimum Moisture Content" test (four readings per test) | No | 5 |  | 0
INVISIBLE FENCING
Supply and Installation of invisible fencing to be 3305mm x 2400mm high, with panel aperture size centres at 76.2x12.7mm, wire diameter at 3.5mm, with 3700 x 85 x 85mm Galvanised metal with polymeric coating posts. The panels shall be reinforced with 4x50mm deep V formation horizontal recessed bands, the panels shall have 2x70 degree flanges along sides, posts shall be 2.4m long taper locking posts. | m | 95 |  | 0
Extra over for gates
1500mm x 2400m single leaf swing gate inclusive of the post | No | 1 |  | 0
WATER RECULATION | H3
Straight pipe
Class 12 PVC-U pressure pipes | H3
63mm diameter Pipes laid in and including trenches exceeding 2m not exceeding 4m deep | m | 225 |  | 0
Extra over Class 12 PVC-U pressure fittings | H4
90 degree bends
63mm diameter | No | 14 |  | 0
45 degree bends
63mm diameter | No | 18 |  | 0
22.5 degree bends
63mm diameter | No | 12 |  | 0
Tee's
63-63-63 mm dia | No | 49 |  | 0
Reducers
Reducer: d= 63mm, d1= 54mm | No | 10 |  | 0
Reducer: d= 54mm, d1= 39mm | No | 13 |  | 0
Isolating valves to be specificied by the engineer
Valves: 63mm | No | 1 |  | 0
Coupling to be specified by the engineer
Coupling: d= 63mm | No | 38 |  | 0
Class 12 PVC-U pressure pipes | H3
95mm diameter Pipes laid in and including trenches exceeding 2m not exceeding 4m deep | m | 574 |  | 0
Extra over Class 12 PVC-U pressure fittings | H4
90 degree bends
95mm diameter | No | 38 |  | 0
45 degree bends
95mm diameter | No | 35 |  | 0
22.5 degree bends
95mm diameter | No | 18 |  | 0
Tee's
95-95-95 mm dia | No | 12 |  | 0
Reducers
Reducer: d= 95mm, d1= 63mm | No | 8 |  | 0
Reducer: d= 63mm, d1= 50mm | No | 12 |  | 0
Isolating valves to be specificied by the engineer
Valves: 95mm | No | 1 |  | 0
Coupling to be specified by the engineer
Coupling: d= 95mm | No | 96 |  | 0
Class 12 PVC-U pressure pipes | H3
110mm diameter Pipes laid in and including trenches exceeding 2m not exceeding 4m deep | m | 251 |  | 0
Extra over Class 12 PVC-U pressure fittings | H4
90 degree bends
110mm diameter | No | 25 |  | 0
45 degree bends
110mm diameter | No | 31 |  | 0
22.5 degree bends
110mm diameter | No | 17 |  | 0
Tee's
110-110-110 mm dia | No | 8 |  | 0
Reducers
Reducer: d= 110mm, d1= 95mm | No | 14 |  | 0
Reducer: d= 95mm, d1= 63mm | No | 12 |  | 0
Isolating valves to be specificied by the engineer
Valves: 110mm | No | 1 |  | 0
Coupling to be specified by the engineer
Coupling: d= 110mm | No | 42 |  | 0
Class 16 PVC-U pressure pipes | H3
95mm diameter Pipes laid in and including trenches exceeding 2m not exceeding 4m deep | m | 298 |  | 0
Extra over Class 16 PVC-U pressure fittings | H4
90 degree bends
95mm diameter | No | 17 |  | 0
45 degree bends
95mm diameter | No | 14 |  | 0
22.5 degree bends
95mm diameter | No | 22 |  | 0
Tee's
95-95-95 mm dia | No | 13 |  | 0
Reducers
Reducer: d= 95mm, d1= 63mm | No | 14 |  | 0
Reducer: d= 63mm, d1= 50mm | No | 10 |  | 0
Isolating valves to be specificied by the engineer
Valves: 95mm | No | 1 |  | 0
Coupling to be specified by the engineer
Coupling: d= 95mm | No | 50 |  | 0
Class 16 PVC-U pressure pipes | H3
75mm diameter Pipes laid in and including trenches exceeding 2m not exceeding 4m deep | m | 298 |  | 0
Extra over Class 16 PVC-U pressure fittings | H4
90 degree bends
95mm diameter | No | 17 |  | 0
45 degree bends
75mm diameter | No | 14 |  | 0
22.5 degree bends
75mm diameter | No | 22 |  | 0
Tee's
75-75-75 mm dia | No | 13 |  | 0
Reducers
Reducer: d= 75mm, d1= 63mm | No | 14 |  | 0
Reducer: d= 63mm, d1= 50mm | No | 10 |  | 0
Isolating valves to be specificied by the engineer
Valves: 75mm | No | 1 |  | 0
Coupling to be specified by the engineer
Coupling: d= 75mm | No | 50 |  | 0
Fanged Gate valves | H4
DN100/PN16 full bore flanged gate valve, ductile iron in accordance to EN558/3 (BS), EN109 and SS stem. Hydraulic pressure to 1.5XPN finishing to be fusion bonded epoxy to GSK and DIN 3476, 250µm. | No | 2 |  | 0
Non-Return Swing (Check Valve)
DN100/PN16 full bore flanged gate valve, ductile iron in accordance to EN558/3 (BS), EN109 and SS stem. Hydraulic pressure to 1.5XPN finishing to be fusion bonded epoxy to GSK and DIN 3476, interinal disc to be fully vulcanized with EPDM rubber and mounted with nylon bushing 250µm Hydraulics test according to EN1205-4 adapters (75mmX80mm) For UPVC to steel flanges to be: blue epoxy coated LM6 galvanized fittings (12 bar) or UPVC when submerged. | No | 2 |  | 0
Y-Strainer
DN100/PN16 flanged Y-strainer with SS screen, ductile iron accordance to EN558 and flanged drilling to EN1092 hydraulic pressure to 1.5XPN finishing to be fusion bonded epoxy coating. | No | 2 |  | 0
Testing and commisioning
Allow an amount for the testing comissioning of the newly installed pipe line | Item | 1 |  | 0
Certificate of Compliance (CoC)
The Contractor shall make provision to issue certiicate of compliance (COC) for the entire installation after commissioning - Standard to be specified by the engineer. | Item | 1 |  | 0
TOTAL-SECTION NO.2 -BILL NO 9- EXTERNAL WORKS |  |  |  | 0
SECTION NO.2 | H1
BUILDING WORK | H1
BILL NO. 10 | H1
PROVISIONAL SUMS
PURIFICATION SYSTEM | H1
SUPPLEMENTARY PREAMBLES
NOTE: Tenderers are referred to the definition of general
attendance on nominated sub-contractors given in Clause 9 of
the Preliminaries
THE FOLLOWING PROVISIONAL SUMS ARE FOR WORK
TO BE EXECUTED BY SELECTED SUBCONTRACTORS
The following Provisional Sums are for specialists work to be
executed by a selected Sub-contractor who upon appointment
in terms of the Conditions of Contract shall be deemed to be a
Domestic Sub-Contractor to the Contractor
A Selected Sub-Contractor shall be a Sub-contractor executing
work for which a sum of money is provided for in the Bills of
Quantities or a Sub-contractor executing additional specialist
work which arises as a result of an instruction by the Principal
Agent/Engineer
Tender documents for such work shall be prepared by the
Principal Agent/Engineer in consultation with and to the
approval of the Contractor and such tender document shall be
issued by the Principal Agent/Engineer to a list of tenderers
agreed upon between the Principal Agent/Engineer and
Contractor.
Tenders shall be submitted to the Principal Agent/Engineer
The Selected Sub-contractor shall be chosen by the Principal
Agent/Engineer and the Contractor, and the Contractor shall
satisfy himself that such selected sub-contractor can meet the
requirements of the Sub-Contract agreement and the
Contractor shall inform the Principal Agent/Engineer
accordingly
The procedure relating to the method of selection, obtaining of
tenders, adjudication thereof and the appointment of the
Selected Sub-contractor shall not create any contractual
relationship between the Client and the Selected
Sub-contractor
NOTE: Under no circumstances may any Prime Cost -
Provisional Amount, etc be extended at an amount higher than
the amount given in the Bill
Allow an amount of R 630 000. 00 (Six Hundred and Thirty Thousand) for the supply and installation of purification system as per Principal Agent's instruction. | Item | 1 |  | 0
Allow an amount for attendance | Item | 1 |  | 0
Allow an amount for profit | Item | 1 |  | 0
TOTAL - SECTION 2 - BILL 10 - PURIFICATION SYSTEM |  |  |  | 0
SECTION NO.2 | H1
BUILDING WORK | H1
BILL NO. 11 | H1
PROVISIONAL SUMS
COMMERCIAL WATER PUMP | H1
SUPPLEMENTARY PREAMBLES
NOTE: Tenderers are referred to the definition of general
attendance on nominated sub-contractors given in Clause 9 of
the Preliminaries
THE FOLLOWING PROVISIONAL SUMS ARE FOR WORK
TO BE EXECUTED BY SELECTED SUBCONTRACTORS
The following Provisional Sums are for specialists work to be
executed by a selected Sub-contractor who upon appointment
in terms of the Conditions of Contract shall be deemed to be a
Domestic Sub-Contractor to the Contractor
A Selected Sub-Contractor shall be a Sub-contractor executing
work for which a sum of money is provided for in the Bills of
Quantities or a Sub-contractor executing additional specialist
work which arises as a result of an instruction by the Principal
Agent/Engineer
Tender documents for such work shall be prepared by the
Principal Agent/Engineer in consultation with and to the
approval of the Contractor and such tender document shall be
issued by the Principal Agent/Engineer to a list of tenderers
agreed upon between the Principal Agent/Engineer and
Contractor.
Tenders shall be submitted to the Principal Agent/Engineer
The Selected Sub-contractor shall be chosen by the Principal
Agent/Engineer and the Contractor, and the Contractor shall
satisfy himself that such selected sub-contractor can meet the
requirements of the Sub-Contract agreement and the
Contractor shall inform the Principal Agent/Engineer
accordingly
The procedure relating to the method of selection, obtaining of
tenders, adjudication thereof and the appointment of the
Selected Sub-contractor shall not create any contractual
relationship between the Client and the Selected
Sub-contractor
NOTE: Under no circumstances may any Prime Cost -
Provisional Amount, etc be extended at an amount higher than
the amount given in the Bill
Allow an amount of R 430 000. 00 (Four Hundred and Thirty Thousand) for the supply and installation of commercial water pump as per Principal Agent's instruction. | Item | 2 |  | 0
Allow an amount for attendance | Item | 2 |  | 0
Allow an amount for profit | Item | 2 |  | 0
TOTAL - SECTION 2 - BILL 11 - COMMERCIAL WATER PUMP |  |  |  | 0
STEEL WATER TANK |  |  |  | 0
SECTION 3: PUMP HOUSE
SECTION 3
BILL No. 1
EARTHWORKS
EXCAVATION, FILLING, ETC
For preambles see "Model Preambles for Trades (2008 Edition)" and Supplementary preambles as specified in the Trades.
---------------------------------------
SUPPLEMENTARY PREAMBLES | H2
Nature of ground | H4
The nature of the ground is assumed to be sandy weathered granite, therefore "earth", but possibly interspersed with "hard rock"
Excavation for working space in rock | H4
Notwithstanding clause 11 page 8 of the Standard System of Measuring Building Work, excavation for working space in rock will be measured in cubic metres to the extent executed and given as "extra over" bulk excavation or trench and hole excavation as the case may be
Carting away of excavated material | H4
Descriptions of carting away of excavated material shall be deemed to include loading excavated material onto trucks directly from the excavations or, alternatively, from stock piles situated on the building site
Filling | H4
Notwithstanding the reference to prescribed multiple handling in clause 1 page 6 of the Standard System of Measuring Building Work, prices for filling and backfilling shall include for all selection and any multiple handling of material
Soil poisoning | H4
Ant and weed poisoning will be applied in accordance to SABS specifications by Registered and Approved Specialists who will issue a five (5) year guarantee. The contractor will only be paid for this items once they have produced the said cerfificate to the Principal Agent
SITE CLEARANCE, ETC. | H2
Site clearance | H3
Digging up and removing rubbish, debris, vegetation, hedges, shrubs and trees not exceeding 200mm girth, bush, etc. | m2 | 48 |  | 0
Excavation not exceeding 2 m in earth below natural, filled and compacted, or reduced ground level, for :
Bulk excavation | m3 | 45 |  | 0
Trenches | m3 | 9 |  | 0
Extra over trench and hole excavations in earth for excavation in: | H4
Soft rock | m3 | 54 |  | 0
Hard rock | m3 | 27 |  | 0
Extra over all excavations for carting away | H4
Surplus material from excavations and/or stock piles on site to a dumping site to be located by the contractor within 20km from the building site | m3 | 135 |  | 0
Imported material compacted to 95% MOD AASHTO Density | H4
G5 imported material in filling carting away surfaces compacted | m3 | 54 |  | 0
Risk of collapse of excavations | H4
Sides of trench and hole excavations not exceeding 1,5m deep | m2 | 40 |  | 0
Keeping excavations free of water
Keeping excavations free of all water other than subterranean water | Item | 1 |  | 0
Earth filling obtained from the excavations and/or prescribed stock piles on site compacted to 90% Mod AASHTO density
Backfilling to trenches, holes, etc | m3 | 5 |  | 0
SOIL POISONING | H4
Soil insecticide
Under floors etc including forming and poisoning shallow furrows against foundation walls etc, filling in furrows and ramming | m2 | 54 |  | 0
TOTAL - SECTION 3 - BILL 1 -EARTHWORKS |  |  |  | 0
SECTION 3
BILL No. 2
CONCRETE, FORMWORK AND REINFORCEMENT
For preambles see "Model Preambles for Trades (2008 Edition)" and Supplementary preambles as specified in the Trades.
---------------------------------------
SUPPLEMENTARY PREAMBLES | H2
Cost of tests | H4
The costs of making, storing and testing of concrete test cubes as required under clause 7 "Tests" of SABS 1200 G shall include the cost of providing cube moulds necessary for the purpose, for testing costs and for submitting reports on the tests to the architect. The testing shall be undertaken by an independent firm or institution nominated by the contractor and to the approval of the architect. (Test cubes are measured separately)
Breeze concrete shall consist of twelve parts clean dry furnace ash, free from coal or other foreign matter, to one part cement (12:1), the ash graded up to particles which will pass a 16,5mm ring from a minimum which fails to pass a 4,75mm mesh. The finer materials from the screening are to be first mixed with the cement into a mortar and the ash added afterwards and thoroughly incorporated
Formwork | H4
Description of formwork shall be deemed to include use and waste only (except where described as "left in" or "permanent"), for fitting together in the required forms, wedging, plumbing and fixing to true angles and surfaces as necessary to ensure easy release during stripping and for reconditioning as necessary before re-use
The vertical strutting shall be carried down to such construction as is sufficiently strong to afford the required support without damage and shall remain in position until the newly constructed work is able to support itself
Formworks to soffits of solid slabs etc shall be deemed to be slabs not exceeding 250mm thick unless otherwise described
Formwork to soffits of slabs, beams, etc shall be deemed to be propped up exceeding 1,5m and not exceeding 3,5m high unless otherwise described
Formwork to sides of bases, pile caps, ground beams, etc will only be measured where it is prescribed by the engineer for design reasons. Formwork necessitated by irregularity or collapse of excavated faces will not be measured and the cost thereof shall be deemed to be included in the allowance for taking the risk of collapse of the sides of the excavations, provision for which is made in "Earthworks"
PRECAST CONCRETE | H2
Concrete lintels | H3
110 x 75mm precast concrete lintels as per the engineers spec. | m | 4 |  | 0
UNREINFORCED CONCRETE
25MPa/19mm concrete | H4
Apron paving cast in panels | m3 | 7 |  | 0
REINFORCED CONCRETE CAST AGAINST EXCAVATED SURFACES | H3
30MPa/19mm concrete | H4
Strip foundations | m3 | 5 |  | 0
REINFORCED CONCRETE | H4
30MPa/19mm concrete
Surface beds cast in panels on waterproofing | m3 | 5 |  | 0
TEST BLOCKS | H4
Making and testing 150 x 150 x 150mm concrete strength test cube | No | 4 |  | 0
CONCRETE SUNDRIES | H4
Finishing top surfaces of concrete smooth with a wood float | m2 | 14 |  | 0
Apron paving to falls | m2 | 32 |  | 0
ROUGH FORMWORK (DEGREE OF ACCURACY II) | H3
Rough formwork to sides | H4
Edges, risers, ends and reveals not exceeding 300mm high or wide | m | 16 |  | 0
MOVEMENT JOINTS ETC | H3
Expansion joints with 12mm polystyrene between vertical surfaces | H4
12mm Joints not exceeding 300mm high between concrete and brick surfaces | m | 16 |  | 0
Saw cut joints | H4
6 x 30mm Saw cut joints in top of concrete | m | 7 |  | 0
REINFORCEMENT | H3
High tensile steel reinforcement to structural concrete work | H4
12mm-16mm Diameter bars | t | 1 |  | 0
Fabric reinforcement | H4
Type 193 fabric reinforcement in surface beds | m2 | 14 |  | 0
TOTAL - SECTION 3 - BILL 2 - CONCRETE, FORMWORK AND REINFORCEMENT |  |  |  | 0
SECTION 3
BILL No. 3
MASONRY
For preambles see "Model Preambles for Trades (2008
Edition)" and Supplementary preambles as specified in the
Trades.
---------------------------------------
SUPPLEMENTARY PREAMBLES | H2
BRICKWORK | H2
Sizes in descriptions | H4
Where sizes in descriptions are given in brick units, "one brick"
shall represent the length and "half brick" the width of a brick
Linings to concrete | H4
Descriptions of linings to concrete, unless otherwise described,
shall be deemed to include wire ties
Hollow walls etc | H4
Descriptions of hollow walls shall be deemed to include wire
ties and leaving every fifth perpend of the bottom course of the
external skin open as a weep hole
Reinforced brick lintels | H4
Lintels shall bear at least 160mm onto adjacent walling. Where
such bearing cannot be obtained due to the proximity of
adjacent openings the lintel shall be continuous
Face bricks | H4
Bricks shall be ordered timeously to obtain uniformity in size
and colour
Pointing | H4
Descriptions of recessed pointing to fair face brickwork and
face brickwork shall be deemed to include square recessed,
hollow recessed, weathered pointing, etc
FOUNDATIONS (PROVISIONAL)
222 x 106 x 73mm Nebraska Travertine Face Brick Standard clay bricks. | H3
Brickwork of NFX bricks (14 MPa nominal compressive strength) in class I mortar | H4
One brick wall | m2 | 8 |  | 0
Brickwork reinforcement | H4
150mm Wide reinforcement built in horizontally | m | 91 |  | 0
Galvanised hoop iron cramps, ties, etc
40 x 1,6mm Wall tie 550mm long with one end shot pinned to concrete and other end built into brickwork | No | 12 |  | 0
Approved face bricks pointed with recessed horizontal and flush vertical joints. 222 x 106 x 73mm Nebraska Travertine Face Brick Standard clay bricks. | H4
Extra over brickwork for face brickwork | m2 | 8 |  | 0
SUPERSTRUCTURE | H3
222 x 106 x 73mm Nebraska Travertine Face Brick Standard clay bricks. | H3
Brickwork of NFX bricks (14 MPa nominal compressive strength) in class I mortar | H4
One brick wall | m2 | 55 |  | 0
BRICKWORK SUNDRIES | H3
Brickwork reinforcement | H4
150mm Wide reinforcement built in horizontally | m | 144 |  | 0
FACE BRICKWORK | H3
EXTERNAL FACE BRICKWORK | H3
Approved face bricks pointed with recessed horizontal and flush vertical joints. 222 x 106 x 73mm Nebraska Travertine Face Brick Standard clay bricks. | H4
Extra over brickwork for face brickwork | m2 | 55 |  | 0
Face brick-on-edge header course lintel 115mm high 115mm wide, pointed on front and door | m | 5 |  | 0
TOTAL - SECTION 3 - BILL 3 - MASONRY |  |  |  | 0
SECTION 3
BILL No. 4
WATERPROOFING
For preambles see "Model Preambles for Trades (2008
Edition)" and Supplementary preambles as specified in the
Trades.
DAMP-PROOFING OF WALLS AND FLOORS
One layer of 375 micron approved embossed damp proof course
In walls | m2 | 5 |  | 0
One layer of 250 micron approved waterproof sheeting sealed at laps with pressure sensitive tape
Under surface beds | m2 | 12 |  | 0
TOTAL - SECTION 3 - BILL 4 - WATERPROOF |  |  |  | 0
SECTION NO.2 | H1
BUILDING WORK | H1
BILL NO.5 | H1
ROOF COVERINGS ETC | H1
For preambles see "Model Preambles for Trades (2008
Edition)" and Supplementary preambles as specified in the
Trades.
---------------------------------------
SUPPLEMENTARY PREAMBLES | H2
General | H4
All roof coverings, etc., to be with a covering of Z275
galvanising. All holes to be drilled and not punched
Where described as with "Chromadek" finish, all sheets,
flashings, etc., shall be with "Chromadek" silicone polyester
paint for exterior use
Sizes | H4
All items are measured net unless otherwise described
Flashings, trimming plates, etc. | H4
Prices to include for all cutting and waste and relevant fixing
material, unless otherwise described
All rates for flashings, trimmings, etc., to include for forming
drips and closed ends to troughs of sheet steel roof covering
where applicable
All items are unless otherwise described measured net
PROFILED METAL SHEETING AND ACCESSORIES | H2
Global roofing solutions 0.53mm thick 406mm cover Klip-lok 406 profifil chromadel Z200 spelter ISQ550 antique red top coat and pebble grey backing coat roof sheeting, fixed to timber intermediate. Purlins at Max 1200mm centres, and eaves and ridge purlins at max 1200mm centres (final spacing to be as per engineer's specifications) using KL clips fixed with 10 No. 11 x 45mm long self-vary drilling wafer head PH2 screw, type 17 drill pomit fasterners (fasteners lengths may vary depending on the insulation used or requirements), all following the manufacturer's specifications by GRS approved contractor or equal. | H4
Roof sheeting | m2 | 22 |  | 0
Narrow flute closer | m | 16 |  | 0
TOTAL - SECTION 2 - BILL 5 - ROOF COVERING |  |  |  | 0
SECTION 3
BILL No. 6
CARPENTRY AND JOINERY
For preambles see "Model Preambles for Trades (2008
Edition)" and Supplementary preambles as specified in the
Trades.
---------------------------------------
SUPPLEMENTARY PREAMBLES | H2
Particle board: | H3
Particle board shall comply with the following specifications:
a) SABS 1300 Particle board: exterior and flooring type
b) SABS 1301 Particle board: interior type
Joinery: | H3
Descriptions of frames shall be deemed to include frames,
transomes, mullions, rails, etc
Descriptions of hardwood joinery shall be deemed to include
pelleting of bolt holes
Fixing | H3
Items described as "nailed" shall be deemed to be fixed with
hardened steel nails or shot pins to brickwork or concrete
Decorative laminate finish: | H3
Laminate finish shall be glued under pressure. Edge strips
shall be butt jointed at junctions with adjacent similar finish
EAVES, VERGES, ETC | H2
Everite medium density plain ungrooved Nutec fascia boards (Code: 41-203), size 300 x 12mm fixed to 38 x 38mm support battens between rafters twice screwed with 12 x 40mm countersunk brass screws at 900mm C/C to support batterns with Chromaprep H-profile fascia joiner between boards and chromaprep H fascia corner joinersat board ends. | H4
Fascia boards | m | 16 |  | 0
ROOF TRUSSES | H3
SAWN HARDWOOD
38 x 114mm wall plate | m | 16 |  | 0
38 x 114mm common rafter with insulation sheet membrane high desity polystyrene block max density 40 kg/m3. 38 x 114 primary WEB bracing supported by joist and joined with punched metal plates gryptite connector plates (110 x 240mm). Secondary WEB 38 x 114mm SA pine bracing grade 10, primary king post 38 x 114 grade 10 SA pine timber at the center of all trusses, truss spacing at minimum of 1200mm C/C and 38 x 73 grade 10 secondary post SA pine timber at all trusses spacing should be confirmed on engineer's designs. Bottom chord 38 x 228mm grade 10 SA pine rested on wall plate with hoop iron straps to engineer's satisfication, 38 x 38mm brandering at minimum 400mm C/C nail punched to joist. 38 x 38mm SA pine purlins at minimum 700mm C/C spacing edged with 50 x 35mm. All members to be joined with punched metal plates gryptite connector plates (110 x 240mm) and mitek type E angle (150 x 150 x 50mm), type F (150 x 100 x 80mm) and approved similar brackets. The length of of one full truss shall not exceed 5000mm. | H4
Full truss not exceeding 5000mm | No | 5 |  | 0
UNDER-TRUSS INSULATIONS | H3
Isover 50mm thick factorylite non-combustible light weight fibreglass, glasswool thermal roof insulation with reinforced foil facing (code: 11408) normal density 12kg/m3, fixed concurrently with the roof covering with galvanized steel straining wires ar 300mm C/C and tied down top and bottom after tensioning with galsvanized hoop iron ties with overlaps stapled together, all in accordance with the manufacturer's recommendations. | H4
Insulation | m2 | 21 |  | 0
DOORS ETC
Wrought meranti doors hung to steel frames
44mm Framed double door in two equal leaves, each leave with horizontal battens on both sides, size 1500 x 2100mm high, hung folding with rebated meeting stiles (D1) | No | 1 |  | 0
TOTAL - SECTION 3 - BILL 6 - CARPENTARY AND JOINERY |  |  |  | 0
SECTION 3
BILL No. 7
IRONMONGERY
For preambles see "Model Preambles for Trades (2008
Edition)" and Supplementary preambles as specified in the
Trades.
---------------------------------------
SUPPLEMENTARY PREAMBLES | H2
Descriptions | H4
Items described as "plugged" shall be deemed to include
screwing to fibre, plastic or metal plugs
Finishes to ironmongery | H4
Where applicable finishes to ironmongery are indicated by
suffixes in accordance with the following list:
BS Satin bronze lacquered CH Chromium plated
SC Satin chromium plated
SE Silver enamelled
GE Grey enamelled
AS Anodised silver
AB Anodised bronze
AG Anodised gold
ABL Anodised black
PB Polished brass
PL Polished and lacquered
PT Epoxy coated
SD Sanded
HINGES, BOLTS, ETC
150mm Lever flush bolts | No | 2 |  | 0
HINGES: Two ball-bearing butt hinges with Stainless Steel finish. | No | 3 |  | 0
LOCKS | H4
Locksets including handles | H4
Double cylinder lockset. | No | 1 |  | 0
HANDLES: Handle on 150 x 45mm pressed backplate with Anodised Silver finish including Euro Profile cylinder upright lock case and 66mm Euro Profile double cylinder. | No | 1 |  | 0
SUNDRIES | H3
DOORSTOP: Aluminium doorstop with anodised Silver finish. | No | 2 |  | 0
LETTERS, NAMEPLATES, ETC | H3
Natural anodised aluminium plates engraved with international pictograms in colour | H4
SIGNAGE: "Name plate" engraved grade 304 Stainless Steel sign, size 150 x 150 x 1,2mm with counter-sunk fixing holes plugged and screwed with aluminium screws. | No | 3 |  | 0
TOTAL - SECTION 3 - BILL 7 - IRONMONGERY |  |  |  | 0
SECTION 3
BILL No. 8
METALWORK
For preambles see "Model Preambles for Trades (2008
Edition)" and Supplementary preambles as specified in the
Trades.
---------------------------------------
Descriptions | H4
Descriptions of bolts shall be deemed to include nuts and
washers
Descriptions of expansion anchors and bolts and chemical
anchors and bolts shall be deemed to include nuts, washers
and mortices in brickwork or concrete
Metalwork described as"holed for bolt(s)" shall be deemed to
exclude the bolts unless otherwise described
Drawings | H4
Tenderers are referred to architect's drawings annexed to this
document for full details of the windows, doors, etc
PRESSED STEEL DOOR FRAMES | H3
1,2mm Rebated frames suitable for one brick walls | H4
Frame for double door 1500 x 2100mm high (D1) | No | 1 |  | 0
TOTAL - SECTION 3 - BILL 8 - METALWORK |  |  |  | 0
SECTION 3
BILL No. 9
PLASTER
For preambles see "Model Preambles for Trades (2017
Edition)" and Supplementary preambles as specified in the
Trades.
SCREEDS | H3
3:1 Cement plaster screeds steel trowelled on concrete | H4
30mm Thick on floors | m2 | 14 |  | 0
INTERNAL PLASTER | H3
15mm smooth wall plaster on brickwork | H4
On walls | m2 | 55 |  | 0
On narrow widths | m2 | 4 |  | 0
TOTAL - SECTION 3 - BILL 9 - PLASTER |  |  |  | 0
TOTAL SECTION 3: PUMP HOUSE |  |  |  | 0
SECTION 4: CONTINGENCIES
SECTION NO.4 | H1
BUILDING WORKS | H3
BILL NO.1 | H1
CONTIGENCIES | H2
Contigencies | H4
Allow 5% of the measured works including P&Gs for the purposes of the contingencies. The contingencies to be used at the discretion of the client supported by the principal agent. | SUM | 1 |  | 0
TOTAL SECTION NO.4 - BILL NO.1 - CONTINGENCIES |  |  |  | 0
SUMMARY
SECTION 1: PRELIMINARIES AND GENERALS |  |  |  | 0
SECTION 2: STEEL WATER TANK |  |  |  | 0
SECTION 3: PUMP HOUSE |  |  |  | 0
SECTION 4: CONTINGENCIES |  |  |  | 0
TOTAL EXCLUDING VAT |  |  |  | 0
VAT @ 15% |  |  |  | 0
TOTAL INCLUDING VAT |  |  |  | 0

## Take Off (hidden)
Foundations
Excavations | 14 | 9.08 | 0.8 | 101.696
Risk of collapse | 14 | 0.8 | 11.2
| 14 | 0.8 | 11.2
| 9.08 | 0.8 | 7.264
| 9.08 | 0.8 | 7.264
36.928
Slotted pipe | 66 | 0.3 | 0.3 | 5.94
Concrete slab | 14 | 9.08 | 0.5 | 63.56
Tappered beams | 0.45 | 0.4 | 9 | 1.62 | 12.96
| 0.45 | 0.4 | 14 | 2.52 | 12.6
precast (400 x 250) | 7.5 | 60
Tappered beams formwork | 9 | 0.45 | 4.05
| 9 | 0.45 | 4.05
| 0.25 | 0.45 | 0.1125
| 0.25 | 0.45 | 0.1125
|  |  | 8.325 | 66.6
| 12 | 0.45 | 5.4
| 12 | 0.45 | 5.4
| 0.25 | 0.45 | 0.1125
| 0.25 | 0.45 | 0.1125
|  |  | 11.025 | 55.125