## GF-SEWER - NEW
THE REFURBISHMENTS AND UPGRADES OF SUB-SURFACE SERVICES (SEWER, WATER & STORMWATER) AT WELKOM CAMPUS
ITEM NO |  |  | QUANTITY | RATE | AMOUNT
SECTION NO. 1
BILL NO. 1
PRELIMINARIES AND GENERAL
BUILDING AGREEMENT AND PRELIMINARIES
The JBCC Principal Building Agreement (Edition 6.2 - May 2018) prepared by the Joint Building Contracts Committee shall be the applicable building agreement, amended as hereinafter described
The JBCC Principal Building Agreement contract data form an integral part of this agreement
The JBCC General Preliminaries (May 2018) published by the Joint Building Contracts Committee for use with the JBCC Principal Building Agreement (Edition 6.2 - May 2018) shall be deemed to be incorporated in these bills of quantities, amended as hereinafter described
The contractor is deemed to have referred to the abovementioned documents for the full intent and meaning of each clause
The clauses in the abovementioned documents are hereinafter referred to by clause number and heading only
Where any item is not relevant to this agreement such item is marked N/A signifying "not applicable"
Where standard clauses or alternatives are not entirely applicable to this agreement such amendments, modifications, corrections or supplements as will apply are given under each relevant clause heading and such amendments, modifications, corrections or supplements shall take precedence notwithstanding anything to the contrary contained in the abovementioned documents
PREAMBLES FOR TRADES
The General Preambles for Trades 2017 published by the Association of South African Quantity Surveyors shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of items fully described in the said General Preambles will be entertained
Supplementary preambles and/or specifications are incorporated in these bills of quantities to satisfy the requirements of this project. Such supplementary preambles and/or specifications shall take precedence over the provisions of the General Preambles
The contractor's prices for all items throughout these bills of quantities shall take account of and include where applicable for all of the obligations, requirements and specifications given in the General Preambles and in any supplementary preambles and/or specifications
STRUCTURE OF THIS PRELIMINARIES BILL
Section A : A recital of the headings of the individual clauses in the aforementioned JBCC Principal Building Agreement
Section B : A recital of the headings of the individual clauses in the aforementioned JBCC General Preliminaries
Section C : Any special clauses to meet the particular circumstances of the project
PRICING OF PRELIMINARIES
Should the contractor select Option A in the contract data for the adjustment of preliminaries, the amounts entered against the relevant items in these preliminaries are to be divided into one or more of the three categories provided namely fixed (F), value related (V) and time related (T)
SECTION A: PRINCIPAL BUILDING AGREEMENT
Interpretation (A1-A7)
1 | Clause 1.0 - Definitions and interpretation | CONT
| Pricing of bills of quantities | CONT
| The contractor is to allow opposite each item for all costs in connection therewith. All prices to include, unless otherwise stated, for all materials, fabrication, conveyance and delivery, unloading, storing, unpacking, hoisting, labour, setting, fitting and fixing in position, cutting and waste (except where to be measured in accordance with the standard system of measurement), patterns, models and templates, plant, temporary works, returning of packaging, duties, taxes (other than Value Added Tax), imposts, establishment charges, overheads, profit and all other obligations arising out of this agreement. Value Added Tax (VAT) is to be separately stated on the summary page of these bills of quantities | CONT
| Items left unpriced will be deemed to be covered in prices against other items throughout these bills of quantities and no claim for any extras arising out of the contractor's omission to price any item will be entertained | CONT
| Prices for all construction equipment, temporary works, services and other items shall include for the supply, maintenance, operating cost and subsequent removal and making good as necessary | CONT
| Abbreviated descriptions | CONT
| The items in these bills of quantities utilise abbreviated descriptions. It is the intention that the abbreviated descriptions be fully described when read with the applicable measuring system and the relevant preambles and/or specifications. However, should the full intent and meaning of any description not be clear, the contractor shall, before submission of his tender, call for a written directive from the principal agent, failing which it shall be assumed that the contractor has allowed in his pricing for materials and workmanship in terms of international best practice | CONT
| Legal status of contractor | CONT
| If the contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons then: | CONT
| Agreement | CONT
| The completed Form of Offer and Acceptance, the completed JBCC® Principal Building Agreement and JBCC® contract data, the contract drawings, the priced document and any other documents reduced to writing and signed by the authorised representatives of the parties | CONT
| Construction Period | CONT
| The period commencing on the date of possession of the site by the contractor and ending on the date of practical completion | CONT
| Interest | CONT
| The interest rates applicable on this contract, whether specifically indicated in the relevant clauses or not, will be the rate as determined by the Minister of Finance from time to time, in terms of section 80(1)(b) of the Public Finance Management Act, 1999 (Act No 1 of 1999), calculated as simple interest, in respect of debts owing to the State, and will be the rate as determined by the Minister of Justice and Constitutional Development from time to time, in terms of section 1(2) of the Prescribed Rate of Interest Act, 1975 (Act No 55 of 1975), calculated as simple interest, in respect of debts owing by the State | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
2 | Clause 2.0 - Law, regulations and notices | CONT
3 | Clause 3.0 - Offer and acceptance F:............................. V:............................ T:............................ | Item | 1 |  | 0
4 | Clause 4.0 - Cession and assignment F:............................. V:............................ T:............................ | Item | 1 |  | 0
5 | Clause 5.0 - Documents | CONT
| Value Added Tax | CONT
| Provision is made in the summary page of these bills of quantities for the inclusion of Value Added Tax (VAT) | CONT
| The priced document shall not be used as a specification or method or a basis for procurement of materials and goods | CONT
| Issue of drawings All drawings for this project will be issued electronically and physically, and the contractor shall be deemed to have received such drawings on the date that such drawings have been dispatched electronically [5.6] | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
6 | Clause 6.0 - Employer's agents | CONT
| Delegated authority | CONT
| The authority of the principal agent to issue contract instructions [17.1] and perform duties for specific aspects of the works is delegated to agents as follows [6.2]. This does not preclude the principal agent from issuing such contract instructions | CONT
| 1. Principal Agent | CONT
| 1.1 Duties : The principal Agent has full authority and obligation to act in terms of this agreement | CONT
| 1.2 Contract instructions [6.2; 17.1] : | CONT
| 1.2.1 Rectification of discrepancies, errors in description or quantity or omission of items in the agreement other than in the JBCC Principal Building Agreement | CONT
| 1.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | CONT
| 1.2.3 The site [13.0] | CONT
| 1.2.4 Compliance with the law, regulations and bylaws [2.1] | CONT
| 1.2.5 Provision and testing of samples of materials and goods and/or of finishes and assemblies of elements of the works | CONT
| 1.2.6 Opening up of work for inspection, removal or re-execution [23.2.4; 26.4.2] | CONT
| 1.2.7 Removal or re-execution of work | CONT
| 1.2.8 Removal or substitution of any materials and goods | CONT
| 1.2.9 Protection of the works | CONT
| 1.2.10 Making good physical loss and repairing damage to the works [23.2.2] | CONT
| 1.2.11 Rectification of defects [21.2] | CONT
| 1.2.12 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion, a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | CONT
| 1.2.13 Expenditure of budgetary allowances, prime cost amounts and provisional sums | CONT
| 1.2.14 Appointment of a subcontractor [14.0; 15.0] | CONT
| 1.2.15 Termination of a nominated n/s subcontractor agreement [14.6] | CONT
| 1.2.16 Work by direct contractors [16.0] | CONT
| 1.2.17 Access by others or previous contractors to remedy defective work | CONT
| 1.2.18 Removal from the site of any person employed on the works | CONT
| 1.2.19 Removal from the site of any person not engaged on or connected with the works | CONT
| 1.2.20 On suspension or termination, protection of the works, removal of construction equipment and surplus materials and goods [29.0] | CONT
| 2. Quantity Surveyor | CONT
| 2.1 Duties [6.2] : The Quantity Surveyor (Agent) is responsible for all measurements, cost control, value engineering, approving costs for contract instructions, valuation, submitting payment claims, inspecting the functionality and quality of the works and all other Quantity Surveying functions | CONT
| 2.2 Contract instructions [6.2; 17.1] : | CONT
| 2.2.1 No contract instructions delegated to the Quantity Surveyor | CONT
| 3. Civil and Structural Engineer | CONT
| 3.1 Duties [6.2] : The Civil and Structural Engineer (Agent) is responsible for the Civil/Structural Engineering design, functional design, approval of specialist work design, quality inspection of the Civil/Structural Engineering works and all other Civil/Structural Engineering functions | CONT
| 3.2 Contract instructions [6.2; 17.1] : | CONT
| 3.2.1 No contract instructions delegated to the Civil/Structural Engineer | CONT
| 4. Mechanical Engineer | CONT
| 4.1 Duties [6.2] : The Mechanical Engineer (Agent) is responsible for the Mechanical Engineering design, functional design, approval of specialist work design, quality inspection of the Mechanical Engineering works and all other Mechanical Engineering functions | CONT
| 4.2 Contract instructions [6.2; 17.1] : | CONT
| 4.2.1 No contract instructions delegated to the Mechanical Engineer | CONT
| 7. Health and safety consultant | CONT
| 7.1 Duties [6.2] : The health and safety consultant (Agent) is responsible for all aspects of health and safety of the works. Without derogating from the generality thereof, the health and safety consultant will perform the following specific functions and duties in respect of the health and safety aspects of the works. He shall: | CONT
| 7.1.1 Act as the employer's agent in terms of the Construction Regulations issued in terms of the Occupational Health and Safety Act,1993 as amended | CONT
| 7.1.2 Prepare and update the health and safety specification for the works | CONT
| 7.1.3 Agree with the contractor the health and safety plan for the works | CONT
| 7.1.4 Carry out regular audits to ensure adherence to the safety plan and compliance with the act and regulations | CONT
| 7.1.5 Through the Principal Agent; stop the execution of the works where the agreed specification or plan is not adhered to | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
7 | Clause 7.0 - Design responsibility F:............................. V:............................ T:............................ | Item | 1 |  | 0
Insurances and securities (A8-A11)
8 | Clause 8.0 - Works risk F:............................. V:............................ T:............................ | Item | 1 |  | 0
| 9.2.7: Replace clause 9.2.7 with this: The employer indemnifies and holds the contractor harmless from all claims or proceedings for damages, expense and/or loss, including legal fees and expenses, in respect of or arising from: Physical loss or damage to an existing structure and the contents thereof due to no fault of the contractor where this agreement is for alterations or additions to an existing structure. Should such an event occur, the contractor shall forthwith give notice to the principal agent | CONT
9 | Clause 9.0 - Indemnities F:............................. V:............................ T:............................ | Item | 1 |  | 0
10 | Clause 10.0 - Insurances F:............................. V:............................ T:............................ | Item | 1 |  | 0
11 | Clause 11.0 - Securities | CONT
12 | Guarantee for payment | N/A
13 | The employer shall provide to the contractor a guarantee for payment in the amount of .......................................................Rand (R...........................) [11.5.1] | N/A
| Clause 11.10 shall be amended as follows: There shall be no lien or right of retention held by any contractor in respect of the works executed on site | CONT
| Extension of waiver of lien | CONT
| The contractor shall ensure that a waiver of lien is included in all subcontracts and that the works executed on the site are kept free of all liens and other encumbrances at all times | CONT
14 | F:............................. V:............................ T:............................ | Item | 1 |  | 0
Execution (A12 - A17)
15 | Clause 12.0 - Obligations of the parties | CONT
| Site establishment The contractor shall provide, maintain, and remove upon practical completion all necessary site establishment facilities. These structures shall be kept clean, orderly, and fit for use at all times [12.2.18] | CONT
| Office accommodation The contractor shall provide, maintain and remove on practical completion air conditioned office accommodation with suitable tables and chairs for meetings to be held on the site. Such offices shall be kept clean and fit for use at all times [12.2.18] | CONT
| Notice board The contractor shall erect in a position approved by the principal agent, maintain and remove on practical completion a notice board recommended by the South African Institute of Architects and as approved by the principal agent listing the names and logos of the employer, the contractor and the professional consultants. No subcontractor or supplier notice boards may be erected unless permission is granted by the principal agent for such notice boards to be erected [12.2.18] | CONT
| Period for the commencement of the works after the contractor takes possession of the site: Seven (7) working days | CONT
| Add the following clause 12.2.22: The contractor is to within fifteen (15) working days of the date of the agreement submit to the principal agent an acceptable health and safety plan, required in terms of the Occupational Health and Safety Act, 1993 (Act No 85 of 1993) | CONT
| Statutory and other notices | CONT
| The contractor shall submit and/or comply with all statutory and other notices that may be required by any local or other authority in order not to cause any delay to the commencement of the works by the contractor. The contractor shall pay all deposits or fees in this regard | CONT
| It is, however, specifically recorded that the employer shall be responsible for the timeous approval of building plans by any local or other authorities and the payment of any fees or charges related thereto | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
16 | Clause 13.0 - Setting out F:............................. V:............................ T:............................ | Item | 1 |  | 0
17 | Clause 14.0 - Nominated subcontractors | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
18 | Clause 15.0 - Selected subcontractors | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
19 | Clause 16.0 - Direct contractors Attendance on direct contractors In respect of direct contractors the contractor shall: | CONT
| 1. Designate an area for the direct contractor to establish a temporary office and workshop and storage of equipment and materials | CONT
| 2. Allow the use of personnel welfare facilities, where provided | CONT
| 3. Provide water, lighting and single phase electric power to a position within 50m of the place where the direct contract work is to be carried out, other than fuel or power for commissioning of any installation | CONT
| 4. Permit the direct contractor to use erected scaffolding, hoisting facilities, etc provided by the contractor, in common with others having the like right, while it remains erected on the site [16.1] | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
20 | Clause 17.0 - Contract instructions Site instructions Instructions issued on site are to be recorded in a site instruction book which is to be supplied and maintained on site by the contractor | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
Completion (A18 - A24)
21 | Clause 18.0 - Interim completion | N/A
22 | Clause 19.0 - Practical completion F:............................. V:............................ T:............................ | Item | 1 |  | 0
23 | Clause 20.0 - Completion in sections | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
24 | Clause 21.0 - Defects liability period and final completion | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
25 | Clause 22.0 - Latent defects liability period F:............................. V:............................ T:............................ | Item | 1 |  | 0
26 | Clause 23.0 - Revision of the date for practical completion Substitution of materials and goods The removal or substitution of any materials and goods which do not conform to the specification or the contract drawings shall not constitute grounds for the extension of the construction period nor for the adjustment of the contract value [17.1.8; 23.1 & 2] | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
27 | Clause 24.0 - Penalty for late or non-completion F:............................. V:............................ T:............................ | Item | 1 |  | 0
Payment (A25 - A27)
28 | Clause 25.0 - Payment | CONT
29 | Clause 25.4, 25.5 and 25.6 are not applicable to this works | N/A
| Clause 25.10 should read as follows: The employer shall pay the contractor the amount certified in an issued payment certificate within thirty (30) calendar days of the date for issue of the payment certificate [CD] including default interest and/or compensatory interest | CONT
30 | Clause 25.11 The contractor shall pay the employer the amount certified in an issued payment certificate within thirty (30) calendar days of the date of issue of the payment certificate [CD] including default interest | CONT
| Clause 25.13 should read as follows: The contractor shall pay all subcontractors within thirty (30) calendar days of the due date for payment by the employer [CD] and on request provide proof thereof to the principal agent within seven (7) calendar days of a request to do so | CONT
| Prices submitted Where prices are submitted by the contractor or subcontractor during the progress of the works in respect of contract instructions or in regard to a claim under the terms of this agreement and notwithstanding the fact that such prices may be used in an interim payment certificate, there is to be no presumption of acceptance. Should the principal agent wish to accept any such prices prior to the issue of the certificate of final completion, it shall be in writing | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
31 | Clause 26.0 - Adjustment of the contract value and final account | CONT
| Fluctuations in costs All fluctuations in costs, with the exception of fluctuations in the rate of Value Added Tax, shall be for the account of the contractor [26.9.5] | CONT
| Tenant installation/user requirements delayed There is a possibility that certain works related to tenant installation/user requirements may have to be delayed and may consequently not be executed prior to practical completion | CONT
| Should the contractor be instructed to do so he shall execute this work under the conditions pertaining to this agreement on the basis that a separate amount for preliminaries appurtenant to this work (if applicable) is agreed to between the contractor and the principal agent and on condition that instruction to proceed with such work is given to him within a period of three (3) calendar months after the date of practical completion of the works | CONT
| The employer reserves the right to omit such work without compensation to the contractor for loss of profit or any other loss which the contractor may suffer as a result of such omission | CONT
| Cost of claims All costs incurred by the contractor in the preparation of claims shall be borne by the contractor. This provision shall not preclude an adjudicator or an arbitrator appointed in terms of this agreement [30.6 & 7] from making a determination on costs | CONT
| Claims from subcontractors The contractor shall review, assess and adjudicate any claims received by him from any subcontractor and thereafter submit same to the principal agent with a recommendation in order to assist the principal agent in adjudicating the claim [26.6] | CONT
| Clause 26.7 should read as follows: The principal agent shall make a fair assessment of the claim [26.6] and adjust the contract value within thirty (30) working days of receipt of such details | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
32 | Clause 27.0 - Recovery of expense and/or loss F:............................. V:............................ T:............................ | Item | 1 |  | 0
Suspension and termination (A28 - A29)
33 | Clause 28.0 - Suspension by the contractor | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
34 | Clause 29.0 - Termination | CONT
| Add clause 29.1.3 as follows: The contractor's estate has been sequestrated, liquidated or surrendered in terms of the insolvency laws in force within the Republic of South Africa | CONT
| Add clause 29.1.4 as follows: The contractor has engaged in corrupt or fraudulent practices in competing for or in executing the contract | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
Dispute resolution (A30)
35 | Clause 30.0 - Dispute resolution F:............................. V:............................ T:............................ | Item | 1 |  | 0
36 | Agreement | CONT
| The required information of the parties and the amount of the contract sum shall be inserted in the agreement for signature of the agreement by the parties F:............................. V:............................ T:............................ | Item | 1 |  | 0
37 | Contract data | CONT
| Tenderer's selections | CONT
| Before submission of his tender the contractor is to complete the tenderer's selections in the contract data | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
SECTION B: GENERAL PRELIMINARIES
Definitions and interpretation (B1)
38 | Clause 1.1 - Definitions F:............................. V:............................ T:............................ | Item | 1 |  | 0
39 | Clause 1.2 - Interpretation F:............................. V:............................ T:............................ | Item | 1 |  | 0
Documents (B2)
40 | Clause 2.1 - Checking of documents F:............................. V:............................ T:............................ | Item | 1 |  | 0
41 | Clause 2.2 - Provisional bills of quantities | CONT
| These bills of quantities are provisionally measured F:............................. V:............................ T:............................ | Item | 1 |  | 0
42 | Clause 2.3 - Availability of construction information | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
43 | Clause 2.4 - Ordering of materials and goods F:............................. V:............................ T:............................ | Item | 1 |  | 0
Previous work and adjoining properties (B3)
44 | Clause 3.1 - Previous work - dimensional accuracy F:............................. V:............................ T:............................ | Item | 1 |  | 0
45 | Clause 3.2 - Previous work - defects F:............................. V:............................ T:............................ | Item | 1 |  | 0
46 | Clause 3.3 - Inspection of adjoining properties F:............................. V:............................ T:............................ | Item | 1 |  | 0
The site (B4)
47 | Clause 4.1 - Handover of site in stages F:............................. V:............................ T:............................ | Item | 1 |  | 0
| The works shall be enclosed in terms of the South African National Standard (SANS) 10400 Part F and as determined by the Architect | CONT
48 | Clause 4.2 - Enclosure of the works F:............................. V:............................ T:............................ | Item | 1 |  | 0
49 | Clause 4.3 - Geotechnical and other investigations F:............................. V:............................ T:............................ | Item | 1 |  | 0
50 | Clause 4.4 - Encroachments F:............................. V:............................ T:............................ | Item | 1 |  | 0
51 | Clause 4.5 - Existing premises occupied F:............................. V:............................ T:............................ | Item | 1 |  | 0
52 | Clause 4.6 - Services - known F:............................. V:............................ T:............................ | Item | 1 |  | 0
Management of contract (B5)
53 | Clause 5.1 - Management of the works F:............................. V:............................ T:............................ | Item | 1 |  | 0
54 | Clause 5.2 - Progress meetings F:............................. V:............................ T:............................ | Item | 1 |  | 0
55 | Clause 5.3 - Technical meetings F:............................. V:............................ T:............................ | Item | 1 |  | 0
Samples, shop drawings and manufacturer's instructions (B6)
56 | Clause 6.1 - Samples of materials F:............................. V:............................ T:........................... | Item | 1 |  | 0
57 | Clause 6.2 - Workmanship samples F:............................. V:............................ T:............................ | Item | 1 |  | 0
58 | Clause 6.3 - Shop drawings F:............................. V:............................ T:............................ | Item | 1 |  | 0
59 | Clause 6.4 - Compliance with manufacturer's instructions F:............................. V:............................ T:............................ | Item | 1 |  | 0
Deposits and fees (B7)
60 | Clause 7.1 - Deposits and fees F:.......................... V:........................... T:......................... | Item | 1 |  | 0
Temporary services (B8)
61 | Clause 8.1 - Water F:............................. V:............................ T:............................ | Item | 1 |  | 0
62 | Clause 8.2 - Electricity F:............................. V:............................ T:............................ | Item | 1 |  | 0
63 | Clause 8.3 - Ablution and welfare facilities F:............................. V:............................ T:............................ | Item | 1 |  | 0
64 | Clause 8.4 - Communication facilities F:............................. V:............................ T:............................ | Item | 1 |  | 0
Prime cost amounts (B9)
65 | Clause 9.1 - Responsibility for prime cost amounts | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
Attendance on subcontractors (B10)
66 | Clause 10.1 - General attendance F:............................. V:............................ T:............................ | Item | 1 |  | 0
67 | Clause 10.2 - Special attendance | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
General (B11)
68 | Clause 11.1 - Protection of the works F:............................. V:............................ T:............................ | Item | 1 |  | 0
69 | Clause 11.2 - Protection/isolation of existing works and works occupied in sections F:............................. V:............................ T:............................ | Item | 1 |  | 0
70 | Clause 11.3 - Security of the works F:............................. V:............................ T:............................ | Item | 1 |  | 0
71 | Clause 11.4 - Notice before covering work F:............................. V:............................ T:............................ | Item | 1 |  | 0
72 | Clause 11.5 - Disturbance | CONT
| Disturbance All work is to be carried out in such a manner as to cause no unacceptable or unreasonable dust, noise, vibrations, nuisance, inconvenience, annoyance and the like to the public, others, other properties and traffic in so far as they exceed the permissible limitations set by government legislation or by the local authority. Any delays, stoppages and the like arising from or in order to comply with the above will not constitute grounds for an adjustment to the construction period or contract value whatsoeverF:........................ V:.........................T:......................... | Item | 1 |  | 0
73 | Clause 11.6 - Environmental disturbance | CONT
| Controlling all forms of pollution The contractor shall be responsible for and take all precautions in controlling by whatever means necessary all forms of pollution emanating from the site during the construction period due inter alia to noise, artificial light, wind-blown sand, dust, deposits of mud, etc | CONT
| The contractor is to ensure that all roads which border the site and are used by the contractor during the execution of the works are kept clean and free of any dirt or debris caused by the execution of the works | CONT
| Insert the following clause if an environmental management plan (EMP) is available and insert the EMP in an annexure | CONT
74 | Environmental management plan The employer has prepared an environmental management plan (EMP) (refer to Annexure 1 for a copy of the relevant plan). The contractor shall price opposite this item for compliance with all the requirements of such EMP F:........................ V:.........................T:......................... | N/A
75 | Clause 11.7 - Works cleaning and clearing F:............................. V:............................ T:............................ | Item | 1 |  | 0
76 | Clause 11.8 - Vermin F:............................. V:............................ T:............................ | Item | 1 |  | 0
77 | Clause 11.9 - Overhand work F:............................. V:............................ T:............................ | Item | 1 |  | 0
78 | Clause 11.10 - Tenant installations F:............................. V:............................ T:............................ | Item | 1 |  | 0
79 | Clause 11.11 - Advertising F:............................. V:............................ T:............................ | Item | 1 |  | 0
SECTION C: SPECIFIC PRELIMINARIES
80 | Warranties for materials and workmanship Where warranties for materials and/or workmanship are called for, the contractor shall obtain a written warranty, addressed to the employer, from the entity supplying the materials and/or executing the work and shall deliver same to the principal agent on final completion of the contract | CONT
| The warranty shall state that workmanship, materials and installation are warranted for a specific period from the date of practical completion and that any defects that may arise during the specified period shall be made good at the expense of the entity supplying the materials and/or doing the work, upon written notice to do so | CONT
| The warranty will not be enforced if the work is damaged by defects in the execution of the works, in which case the responsibility for replacement shall rest entirely with the contractor F:............................. V:............................ T:............................ | Item | 1 |  | 0
81 | Overtime Should overtime be required to be worked for any reason whatsoever, the cost of such overtime is to be borne by the contractor unless the principal agent has specifically authorised, prior to execution thereof, that costs for such overtime are to be borne by the employer F:........................ V:.........................T:......................... | Item | 1 |  | 0
82 | Cooperation of the contractor for cost management It is specifically agreed that the contractor accepts the obligation of assisting the principal agent in implementing proper cost management. The contractor will be advised by the principal agent of all cost management procedures which will be implemented to ensure that the contract value does not exceed the budget F:........................ V:.........................T:......................... | Item | 1 |  | 0
83 | Overloading The contractor shall take all necessary steps to ensure that no damage occurs due to overloading of any portion of the works or temporary works, etc. The contractor shall submit details of his proposed loading, storage, plant erection, etc to the principal agent for approval prior to proceeding with such loading, storing or erecting and shall comply with and pay for the principal agent's requirements in connection with the provision of temporary support work, etc. Any damage caused to the works by overloading shall be made good by the contractor at his sole expense F:........................ V:.........................T:......................... | Item | 1 |  | 0
84 | Propping of floors below The contractor is advised that propping of floors below may be required if he wishes to use any areas of completed suspended reinforced concrete slabs for vehicle access, storage of materials and goods and location of plant, scaffolding, etc. The location of these areas and any necessary propping shall be approved by the principal agent and the cost thereof shall be borne by the contractor F:........................ V:.........................T:......................... | N/A
85 | Testing of flat roof waterproofing for watertightness Flat roof waterproof areas shall be flooded and kept "ponded" for at least forty eight (48) hours as a test to ensure the watertightness of the waterproofing and before any further construction work is carried out above the waterproofing F:........................ V:.........................T:......................... | N/A
86 | Health and safety | CONT
| Without limiting the generality of the provisions of clause 2.0, the contractor's attention is drawn to the provisions of the Construction Regulations issued in terms of the Occupational Health and Safety Act, 1993 as amended. It is specifically stated that the employer shall prepare a documented health and safety specification for the works and that the employer shall ensure that the contractor has made provision for the cost of health and safety measures during the execution of the works. The contractor shall price opposite this item and on the following items for compliance with the act and the regulations and the provisions of the aforementioned health and safety specification [2.1] | CONT
| The contractor shall: 1. Comply with the health and safety specification for the works 2. Prepare, compile and agree with the health and safety consultant the health and safety plan for the works as per the Site Health and Safety Specifications (Once off) 3. Allow for the preparation of site specific Health and Safety file including notifying the authorities of the construction project (Once off) 4. Cooperate with the health and safety consultant in all respects 5. Manage the compliance of all subcontractors with the regulations and with the health and safety plan and specification 6. Conform to the conditions contained in the employer's health and safety specification 7. Provide personal protective clothing and equipment (PPE) per employee (Dust masks, gloves, safety googles, etc) 8. Have a once off on-site Health and Safety training (Health & Safety Rep, First Aider, HIRA, Incident Investigator, Fire Fighter, etc) 9. Do a once off pre-employment, annual and exit medical examination of fitness 10. Have a fully time Safety Officer (Fully registered with the SACPCMP as a CHS0) 11. Provide wheely bins for waste and disposal for hazardous biological waste 12. Have chemical spill kits 13. Provide first aid boxes & signage 14. Have signage, information display and barricading 15. Make a provision for a Health and Safety Representative | CONT
| F:............................. V:............................ T:............................ | Item | 1 |  | 0
87 | Green star building certification F:........................ V:.........................T:......................... | Item | 1 |  | 0
88 | Broad based black economic empowerment (BBBEE) Tenders submitted will be evaluated taking into account their empowerment rating The employer will be monitoring the broad based black economic empowerment (BBBEE) status of the contractor throughout the execution of the works | CONT
| The contractor is to submit to the principal agent on an annual basis a schedule of spend, split into vendors engaged as subcontractors and suppliers indicating their BBBEE rating including proof of the said rating F:........................ V:.........................T:......................... | Item | 1 |  | 0
Community Liaison Officer (CLO)
89 | Make a provision for a CLO and profit and attendance per month for the duration of the project proposed by the contractor | Item | 1 |  | 0
Social Facilitator
90 | Make a provision for a Social Facilitator and profit and attendance per month for the duration of the project proposed by the contractor | Item | 1 |  | 0
Students Practical Training
91 | Make a provision for profit and attendance to integrate plumbing students onto your site and provide them with practical training, resources, and tools of trade. Student stipends shall be borne by the college. This allowance is to be for the duration of the project proposed by the contractor | Item | 1 |  | 0
Confidentiality
92 | Advertising rights The employer may elect to contract with advertising agencies for the erection of advertising hoardings, banners, wraps or the like for the duration of the contract. The contractor shall not prevent such an arrangement and will assist in the facilitation of same. The position and type of advertising structure to be agreed with the principal agent so as not to hinder the contractor in meeting his obligations under this agreement F:........................ V:.........................T:......................... | Item | 1 |  | 0
93 | Confidentiality The contractor undertakes to maintain in confidence any and all information regarding this project and shall obtain appropriate similar undertakings from all subcontractors and suppliers. Such information shall not be used in any way except in connection with the execution of the works No information regarding this project shall be published or disclosed without the prior written consent of the employer F:........................ V:.........................T:......................... | Item | 1 |  | 0
94 | Media releases All rights of publication of articles in the media, together with any advertising relating thereto or in any way connected with this project, shall vest with the employer The contractor together with his subcontractors shall not, without the prior written consent of the employer, cause any statement or advertisement connected with this project to be printed, screened or aired by the media F:........................ V:.........................T:......................... | Item | 1 |  | 0
SUMMARY OF CATEGORIES
Category : Fixed R........................................ Category : Value R........................................ Category : Time R........................................
| TOTAL- SECTION 1- BILL NO.1 - PRELIMINARIES AND GENERAL |  |  |  | 0
SECTION NO. 2
BILL NO. 1
ALTERATIONS
WORK GROUP ALLOCATION
Unless otherwise stated, all items in this Bill will be allocated to Alterations
PREAMBLES
The General Preambles for Trades (2017 edition), as published by the Association of South African Quantity Surveyors, shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of items, fully described in the said General Preambles, will be entertained
The following "Supplementary Preambles" are incorporated in this bill to satisfy the requirements of the project and shall take precedence over the provisions of the said General Preambles
SUPPLEMENTARY PREAMBLES
View site
Before submitting his tender, the tenderer shall visit the site and satisfy himself as to the nature and extent of the work to be done and the value of the materials salvageable from the alterations. No claim for any variations of the contract sum in respect of the nature and extent of the work or of inferior or damaged materials will be entertained
Explosives
No explosives whatsoever may be used for alteration purposes unless otherwise stated
General
The contractor shall carry out the whole of the works with as little mess and noise as possible and with a minimum of disturbance to tenants in the building and to adjoining premises and their tenants. He shall provide proper protection and provide, erect and remove when directed, any temporary tarpaulins that may be necessary during the progress of the works, all to the satisfaction of the principal agent
Materials or articles from alterations that are described as to be "handed over to the Employer", shall be taken to mean "handed over by the Contractor to the Principal Agent" and such materials or articles shall be properly stored by the Contractor until handing over thereof and shall include all necessary transport The Contractor must obtain an official receipt from the Principal Agent listing the materials or articles and dates of handing over Should the Contractor fail to submit the receipt when requested to do so, it shall be deemed that the materials or articles are still in his possession and he will be held liable to the Employer for the full replacement value thereof, which amount will be deducted from any monies due to the Contractor
Making good of finishes shall include making good of the brick and concrete surfaces onto which the new finishes are applied, where necessary
The contractor will be required to take all dimensions affecting the existing buildings and works on the site and he will be held solely responsible for the accuracy of all such dimensions where used in the manufacture of new items
REMOVAL OF EXISTING WORK
Breaking up and removing reinforced concrete, including cutting off and removing reinforcement
1 | 300mm Thick surface beds | m² | 128 |  | 0
Breaking down and removing brickwork, concrete, foundations, etc
2 | One brick walls | m² | 550 |  | 0
Removing precast manholes of various sizes, etc including foundations and earthworks surround
3 | Manhole exceeding 750mm and not exceeding 1500mm diameter with maximum depth of 2000mm | m² | 29 |  | 0
Breaking up and removing bituminous surfacing (Tarmacadam)
4 | 35mm Asphalt | m² | 300 |  | 0
Hacking up/off and removing ceramic tiles including removing mortar bed or adhesive from concrete or brickwork and preparing surfaces for new screed, plaster, tile finish, etc
5 | Tiles to floors | m² | 98 |  | 0
Hacking up/off and removing paving blocks and preparing surfaces for new paving blocks,etc
6 | 60mm Paving blocks | m² | 400 |  | 0
Taking out and removing piping, pipe fittings, valves, taps, traps, pipe supports, etc including cutting off as necessary, holderbats and making good floor and wall finishes
7 | Concrete piping exceeding 300mm and not exceeding 400mm external diameter | m | 1429 |  | 0
8 | PVC piping exceeding 160mm and not exceeding 200mm external diameter | m | 350 |  | 0
PREPARATORY WORK TO EXISTING SERVICES
9 | Cleaning channels, drains and pipes and manholes | m² | 350 |  | 0
| TOTAL - SECTION NO. 2 - BILL NO. 1 - ALTERATIONS |  |  |  | 0
SECTION NO. 2
BILL NO. 2
EARTHWORKS (PROVISIONAL)
WORK GROUP ALLOCATION
Unless otherwise stated, all items in this Bill will be allocated to Earthworks
PREAMBLES
The General Preambles for Trades (2017 edition), as published by the Association of South African Quantity Surveyors, shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of items, fully described in the said General Preambles, will be entertained
The following "Supplementary Preambles" are incorporated in this bill to satisfy the requirements of the project and shall take precedence over the provisions of the said General Preambles
SUPPLEMENTARY PREAMBLES
Nature of ground
The nature of the ground is assumed to be gravel, therefore "earth", but possibly interspersed with "soft rock" or "hard rock"
"Hard rock": granite, quartzitic sandstone or rock of similar hardness, the removal of which requires drilling, wedging and splitting, or the use of explosives
"Soft rock": hard material, the removal of which warrants the use of pneumatic tools and includes hard shale, ferricrete, compact ouklip and material of similar hardness
"Earth": all ground other than that classified as "hard rock" or "soft rock", including made-up ground and loose stones or concrete pieces not exceeding 0.03m3 in volume
Subterranean water
No subterranean water is expected. The water table is expected to vary between approximately 60m and 100m below natural ground level. The removal of subterranean water is given separately
Carting away of excavated material
Descriptions of carting away of excavated material shall be deemed to include loading excavated material onto trucks directly from the excavations or, alternatively, from stock piles situated on the building site
Filling and layer work materials
References such as "G1", "G2", etc in descriptions of filling and layer work materials refer to corresponding references in the document "Guidelines for Road Construction Materials. TRH 14 : 1985" compiled by the Committee of State Road. Authorities and the properties set out therein for each kind shall be applicable to the respective materials described hereinafter
Filling shall be compacted to the prescribed percentage Mod AASHTO density
Trenches shall be carefully backfilled
Cleaning-up of disturbed areas
The contractor will be liable to, upon completion, to rehabilitate all those areas of the site used for spoiling, mixing of concrete or any other disturbances caused to the site by the contractor by grading the area to follow the adjacent ground contours and afterwards compacted to 80% Mod AASHTO density, all to the full satisfaction of the principal agent
Weed Killers, Insecticides, etc
Soil poisoning will be applied in accordance to SABS specifications by Registered and Approved Specialists who will issue a five (5) year guarantee. The contractor will only be paid for this item once they have produced soil poisoning certificate and specified guarantee to the Principal Agent
SITE CLEARANCE
Site clearance
1 | Digging up and removing rubbish, debris, vegetation, hedges, shrubs, bush, etc and trees not exceeding 200mm girth | m² | 1133 |  | 0
REMOVAL OF TREES ETC
Cutting down and removing, grubbing up roots, filling in holes and compacting to 90% Mod AASHTO density
2 | Tree exceeding 200mm and not exceeding 500mm girth | No | 6 |  | 0
EXCAVATION, FILLING, ETC OTHER THAN BULK
Excavation in earth not exceeding 2m deep
3 | Trenches | m³ | 3271 |  | 0
4 | Holes | m³ | 402 |  | 0
5 | Compacted material | m³ | 2 |  | 0
Extra over trench and hole excavations in earth for excavation in
6 | Soft rock | m³ | 367 |  | 0
7 | Hard rock | m³ | 184 |  | 0
Extra over all excavations for carting away
8 | Surplus material from excavations and/or stock piles on site, to a dumping site to be located by the contractor | m³ | 3078 |  | 0
Risk of collapse of excavations
9 | Sides of trench and hole excavations exceeding 1,5m deep | m² | 5837 |  | 0
Keeping excavations free of water
10 | Keeping excavations free of all water other than subterranean water | Item | 1 |  | 0
FILLING ETC
Earth filling obtained from the excavations, compacted to 87% Mod AASHTO density
11 | Earth filling obtained from the excavations, including haulage approximately 20m from the perimeter of the excavations (not compacted) In prescribed stock piles on site | m³ | 1042 |  | 0
Filling of gravel-soil material (G8) supplied by the contractor, compacted to 87% Mod AASHTO density
12 | Backfilling to trenches, holes, etc | m³ | 1051 |  | 0
Filling of gravel-soil material (G7) supplied by the contractor, compacted to 80% Mod AASHTO density
13 | Backfilling to trenches, holes, etc | m³ | 716 |  | 0
Filling of natural gravel material (G6) supplied by the contractor, compacted to 93% Mod AASHTO density
14 | Backfilling to trenches, holes, etc | m³ | 339 |  | 0
Filling of natural gravel material (nominal stone) supplied by the contractor, compacted to 93% Mod AASHTO density
15 | Backfilling of 150mm layer to trenches, holes, etc with 19mm nominal uniformly crushed aggregate | m³ | 221 |  | 0
Compaction of ground surfaces
16 | Compaction of natural or excavated ground surface under floors etc, including scarifying for a depth of 150mm, breaking down oversize material, adding suitable material where necessary and compacting to 87% Mod AASHTO density | m² | 14769 |  | 0
WEED KILLERS, INSECTICIDES, ETC
Soil insecticide in accordance with SANS 5859
17 | To bottoms and sides of trenches etc | m² | 7319 |  | 0
TESTS
Prescribed tests to determine degree of compaction or other properties of ground or filling
18 | Modified AASHTO Density test | No | 100 |  | 0
| TOTAL - SECTION NO. 2 - BILL NO. 2 - EARTHWORKS |  |  |  | 0
SECTION NO. 2
BILL NO. 3
CONCRETE, FORMWORK AND REINFORCEMENT
WORK GROUP ALLOCATION
Unless otherwise stated, all items in this Bill will be allocated to Concrete, Formwork and Reinforcement
PREAMBLES
The General Preambles for Trades (2017 edition), as published by the Association of South African Quantity Surveyors, shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of items, fully described in the said General Preambles, will be entertained
The following "Supplementary Preambles" are incorporated in this bill to satisfy the requirements of the project and shall take precedence over the provisions of the said General Preambles
SUPPLEMENTARY PREAMBLES
Cost of tests
The costs of making, storing and testing of concrete test cubes as required under clause 7 "Tests" of SABS 1200 G shall include the cost of providing cube moulds necessary for the purpose, for testing costs and for submitting reports on the tests for approval. The testing shall be undertaken by an approved independent firm or institution nominated by the contractor (test cubes are measured separately)
Formwork
Descriptions of formwork shall be deemed to include use and waste only (except where described as "left in" or "permanent"), for fitting together in the required forms, wedging, plumbing and fixing to true angles and surfaces as necessary to ensure easy release during stripping and for reconditioning as necessary before re-use
The vertical strutting shall be carried down to such construction as is sufficiently strong to afford the required support without damage and shall remain in position until the newly constructed work is able to support itself
Formwork necessitated by irregularity or collapse of excavated faces will not be measured and the cost thereof shall be deemed to be included in the allowance for taking the risk of collapse of the sides of the excavations, provision for which is made in "Earthworks"
UNREINFORCED CONCRETE CAST AGAINST EXCAVATED SURFACES
20MPa/13mm concrete
1 | Foundation (Benching) | m³ | 10 |  | 0
20MPa/19mm concrete
2 | Foundation (Encasing) | m³ | 5 |  | 0
REINFORCED CONCRETE CAST AGAINST EXCAVATED SURFACES
25MPa/19mm concrete
3 | Slab | m³ | 56 |  | 0
4 | Rodding Eye Encasement | m³ | 4 |  | 0
20MPa/19mm concrete
5 | Slab | m³ | 35 |  | 0
6 | Spacers | m³ | 28 |  | 0
7 | Manhole surround | m³ | 8 |  | 0
TEST CUBES
8 | Making and testing 150 x 150 x 150mm concrete strength test cube (Provisional) | No | 120 |  | 0
CONCRETE SUNDRIES
Finishing top surfaces of concrete smooth with a wood float
9 | Surface beds, slabs, etc to falls and currents | m² | 250 |  | 0
ROUGH FORMWORK (DEGREE OF ACCURACY III)
Rough formwork to sides
10 | Slabs | m² | 85 |  | 0
REINFORCEMENT
High tensile steel reinforcement to structural concrete work
11 | 10mm Diameter bars | t | 5 |  | 0
12 | 12mm Diameter bars | t | 5 |  | 0
13 | 16mm Diameter bars | t | 8 |  | 0
| TOTAL SECTION NO. 2 BILL NO. 3 - CONCRETE. FORMWORK AND REINFORCEMENT |  |  |  | 0
SECTION NO. 2
BILL NO. 4
TILING
WORK GROUP ALLOCATION
Unless otherwise stated, all items in this Bill will be allocated to Tiling
PREAMBLES
The General Preambles for Trades (2017 edition), as published by the Association of South African Quantity Surveyors, shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of items, fully described in the said General Preambles, will be entertained
The following "Supplementary Preambles" are incorporated in this bill to satisfy the requirements of the project and shall take precedence over the provisions of the said General Preambles
SUPPLEMENTARY PREAMBLES
Patterns
Unless otherwise described, tiles shall be laid with continuous joints in both directions
Fixing
Unless described as "fixed with adhesive to plaster (plaster elsewhere)" descriptions of tiling on brick or concrete walls, columns, etc shall be deemed to include 1:4 cement plaster backing and descriptions of tiling on concrete floors etc shall be deemed to include 1:3 plaster bedding
Ceramic, porcelain, marble and granite tiles are to be fixed and grouted with suitable adhesives and grouts as recommended by the manufacturer of the tiles
FLOOR TILING
200 x 200 x 8mm ceramic floor tiles fixed with adhesive to screed (screed elsewhere) and flush pointed with tinted waterproof grout (Tile to match existing)
1 | On floors and landings | m² | 98 |  | 0
SUNDRIES
Aluminium dividing strips
2 | 40 x 5mm Flat section dividing strips between tiles | m | 70 |  | 0
| TOTAL SECTION NO. 2 BILL NO. 4 - TILING |  |  |  | 0
SECTION NO. 2
BILL NO. 5
PLUMBING AND DRAINAGE (PROVISIONAL)
WORK GROUP ALLOCATION
Unless otherwise stated, all items in this Bill will be allocated to Plumbing and Drainage
PREAMBLES
The General Preambles for Trades (2017 edition), as published by the Association of South African Quantity Surveyors, shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of items, fully described in the said General Preambles, will be entertained
The following "Supplementary Preambles" are incorporated in this bill to satisfy the requirements of the project and shall take precedence over the provisions of the said General Preambles
SUPPLEMENTARY PREAMBLES
Stormwater channels
Descriptions of channels shall be deemed to include necessary excavation, surface preparation, compaction, etc, and disposal of surplus material on site
Septic tanks
Descriptions of proprietary type septic tanks shall be deemed to include excavation, bedding and jointing, concrete base slabs, jointing to drains and backfilling, compaction, etc all in accordance with the manufacturer's instructions and disposal of surplus material on site
Reducing fittings
Where fittings have reducing ends or branches they are described as "reducing" and only the largest end or branch size is given. Should the contractor wish to use other fittings and bushes or reducers he may do so on the understanding that no claim in this regard will be entertained
Fixing of pipes
Unless specifically otherwise stated, descriptions of pipes shall be deemed to include fixing to walls, etc, casting in, building in or suspending not exceeding 1m below suspension level
Paper wrapping to pipes
Pipes chased into brickwork must be wrapped with two layers of stout brown paper tied with wire. Rates are to include for wrapping around joints and fittings
Grease impregnated petrolatum anti-corrosion tape
Pipes to be taped shall be coated with the appropriate primer and the tape shall be applied in the appropriate widths. Couplings and fittings to pipes shall be taped in strict accordance with the manufacturer's instructions
Prices for wrapping of pipes shall include for all work as described to couplings in the length
Laying, backfilling, bedding, etc of pipes
Where no manufacturers' instructions exist, pipes shall be laid in accordance with the relevant section of SANS 2001
General
Descriptions of cast iron roof outlets shall be deemed to include joints to pipes and casting into concrete (adaptors for joints to PVC pipes, etc are given separately) Descriptions of overflow pipes where measured in number, shall be deemed to include joints to cisterns and splay cut ends
Descriptions of service pipes and flexible connecting pipes shall be deemed to include connections to taps, cisterns, etc and to steel pipes (adaptors for connections to copper pipes, etc are given separately)
As-built drawings
Where required, the contractor shall prepare an updated set of as-built drawings. At completion of the contract the contractor shall hand these drawings to the principal agent for reproducing onto the originals for handing over to the employer (provision for allowance of as-built drawings elsewhere)
SOIL DRAINAGE
1 | Sand filling in bedding under pipes | m³ | 205 |  | 0
Normal duty PVC sewer channels including wood float, etc
2 | 200mm Channels in bottoms of inspection chambers | m | 48 |  | 0
Extra over normal duty PVC sewer channels for fittings
3 | 200mm 45° Bend | No | 30 |  | 0
4 | 200mm 45° Junction | No | 9 |  | 0
5 | 200mm 45° Double junction | No | 4 |  | 0
Heavy duty (Class 34) PVC sewer pipes installed in accordance with drawing GLDF_002_CIV_SEWER_04_R00
6 | 110mm Pipes laid in trenches (trenches elsewhere) | m | 95 |  | 0
Extra over heavy duty (Class 34) PVC sewer pipes for fittings
7 | 110mm 45° Bend | No | 2 |  | 0
8 | 110mm 45° Junction | No | 2 |  | 0
9 | 110mm x 100mm 45° socketed access reducing junction | No | 3 |  | 0
10 | 110mm 45° single socket radius bend | No | 3 |  | 0
11 | 110mm 45° double socket bend | No | 3 |  | 0
12 | 110mm 45° Rodding eye | No | 1 |  | 0
Heavy duty (Class 34) PVC sewer pipes installed in accordance with drawing GLDF_002_CIV_SEWER_04_R00
13 | 160mm Pipes laid in trenches (trenches elsewhere) | m | 303 |  | 0
Extra over heavy duty (Class 34) PVC sewer pipes for fittings
14 | 160mm 22,5° Bend | No | 3 |  | 0
15 | 160mm 45° Bend | No | 11 |  | 0
16 | 110mm 45° Bend | No | 1 |  | 0
17 | 160mm 90° Bend | No | 1 |  | 0
18 | 160mm 45° Junction | No | 1 |  | 0
19 | 110mm 45° Junction | No | 1 |  | 0
20 | 160mm 45° Reducing junction | No | 9 |  | 0
21 | 160mm x 100mm 45° socketed access reducing junction | No | 7 |  | 0
22 | 160mm 45° single socket radius bend | No | 7 |  | 0
23 | 160mm 45° double socket bend | No | 7 |  | 0
24 | 160mm 45° Rodding eye | No | 2 |  | 0
Heavy duty (Class 34) PVC sewer pipes installed in accordance with drawing GLDF_002_CIV_SEWER_04_R00
25 | 200mm Pipes laid in trenches (trenches elsewhere) | m | 87 |  | 0
Extra over heavy duty (Class 34) PVC sewer pipes for fittings
26 | 200mm x 100mm 45° socketed access reducing junction | No | 2 |  | 0
27 | 200mm 45° single socket radius bend | No | 2 |  | 0
28 | 200mm 45° double socket bend | No | 2 |  | 0
Heavy duty (Class 34) PVC sewer pipes installed in accordance with drawing GLDF_002_CIV_SEWER_04_R00
29 | 250mm Pipes laid in trenches (trenches elsewhere) | m | 392 |  | 0
Extra over heavy duty (Class 34) PVC sewer pipes for fittings
30 | 250mm 45° Bend | No | 3 |  | 0
31 | 110mm 45° Bend | No | 1 |  | 0
32 | 250mm 45° Junction | No | 1 |  | 0
33 | 110mm 45° Junction | No | 1 |  | 0
34 | 250mm 45° Reducing junction | No | 2 |  | 0
35 | 250mm x 100mm 45° socketed access reducing junction | No | 4 |  | 0
36 | 250mm 45° single socket radius bend | No | 4 |  | 0
37 | 250mm 45° double socket bend | No | 4 |  | 0
38 | 250mm 45° Rodding eye | No | 1 |  | 0
Heavy duty (Class 34) PVC sewer pipes installed in accordance with drawing GLDF_002_CIV_SEWER_04_R00
39 | 255mm Pipes laid in trenches (trenches elsewhere) | m | 32 |  | 0
Heavy duty (Class 34) PVC sewer pipes installed in accordance with drawing GLDF_002_CIV_SEWER_04_R00
40 | 315mm Pipes laid in trenches (trenches elsewhere) | m | 40 |  | 0
Extra over heavy duty (Class 34) PVC sewer pipes for fittings
41 | 315mm 45° Reducing junction | No | 1 |  | 0
Heavy duty (Class 34) PVC sewer pipes installed in accordance with drawing GLDF_002_CIV_SEWER_04_R00
42 | 355mm Pipes laid in trenches (trenches elsewhere) | m | 36 |  | 0
Heavy duty (Class 34) PVC sewer pipes installed in accordance with drawing GLDF_002_CIV_SEWER_04_R00
43 | 450mm Pipes laid in trenches (trenches elsewhere) | m | 87 |  | 0
Heavy duty (Class 34) PVC temporary sewer pipes installed in accordance with drawing GLDF_002_CIV_SEWER_04_R00
44 | 450mm Pipes laid in trenches (trenches elsewhere) | m | 309 |  | 0
Extra over heavy duty (Class 34) PVC temporary sewer pipes for fittings
45 | 450mm 45° Bend | No | 2 |  | 0
46 | 450mm 90° Bend | No | 1 |  | 0
47 | 450mm 45° Junction with inspection hatch | No | 3 |  | 0
48 | 450mm 90° Reducing junction with inspection hatch | No | 1 |  | 0
49 | Stop Ends | No | 3 |  | 0
Precast concrete circular inspection chambers with covers and frames installed and sealed in accordance of drawing number GLDF_002_CIV_SEWER_02_R00 (covers and channels elsewhere)
50 | 1000mm Diameter inspection chamber 1600mm deep internally | No | 7 |  | 0
51 | 1000mm Diameter inspection chamber 2000mm deep internally | No | 22 |  | 0
Septic tanks
52 | SABS 1904 standard 12500 litre PVC septic tank | No | 1 |  | 0
53 | SABS Standard honeysucker truck hire for disposal of waste | No | 11 |  | 0
SUNDRIES
54 | 25MPa/19mm Unreinforced concrete in thrust blocks in trenches at bends, tees, etc including extra excavation, formwork, etc | m³ | 24 |  | 0
55 | Extra over Class 34 Heavy Duty PVC for kimberley sockets for fittings | No | 100 |  | 0
Municipal connection
56 | Provide the sum of R20 000.00 (Twenty Thousand Rand Only) for municipal connection | Item | 1 |  | 0
57 | Profit | Item | 1 |  | 0
Testing
58 | Testing soil drainage system | Item | 1 |  | 0
AS-BUILT DRAWINGS
59 | Provision of as-built drawings | Item | 1 |  | 0
| TOTAL SECTION NO. 2 BILL NO. 5 - PLUMBING AND DRAINAGE (PROVISIONAL) |  |  |  | 0
1 | Alterations |  |  |  | 0
2 | Earthworks |  |  |  | 0
3 | Concrete, formwork + reinfmnt |  |  |  | 0
4 | Tiling |  |  |  | 0
5 | Plumbing and drainage |  |  |  | 0
0
SECTION NO. 3
BILL NO. 1
EXTERNAL WORK
WORK GROUP ALLOCATION
Unless otherwise stated, all items in this Bill will be allocated to External work
PREAMBLES
The General Preambles for Trades (2017 edition), as published by the Association of South African Quantity Surveyors, shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of items, fully described in the said General Preambles, will be entertained
The following "Supplementary Preambles" are incorporated in this bill to satisfy the requirements of the project and shall take precedence over the provisions of the said General Preambles
SUPPLEMENTARY PREAMBLES
Precast concrete block road surfacing
Paving shall be laid in accordance with SABS 1200 MJ, SANS 1058 and the Concrete Masonry Association's specifications
Paving shall be laid to herringbone "V" pattern on 20mm thick (thickness after final compaction) clean river sand (preparation of ground or filling elsewhere)
Clean sand shall be swept into joints between roadstones at completion
LANDSCAPING
Ground preparation, filling with garden soil, compost and planting of grass to match existing
1 | Grass | m² | 101 |  | 0
ROADWORK, PARKING AREAS AND PAVING
Additional tests required by the principal agent
2 | Maximum dry density and optimum moisture content test in accordance with method A7 of TMH1 | No | 100 |  | 0
60 mm paving blocks, Shape S-A Class 30/2.0 (in accordance with SANS 1058 latest edition) on 20 mm bedding sand (COLTO 7302(a) ) with joints filled in with sand, compacted with a vibration compactor
3 | Paving to sidewalks etc to falls, including necessary straight edge blocks | m² | 400 |  | 0
Bituminous premix road surfacing
4 | 35mm continuous graded medium grade asphalt surfacing (AC) | m² | 300 |  | 0
Paintwork
Two coats reflective road marking paint on tarmacadam
5 | Line 500mm wide | m | 962 |  | 0
| TOTAL SECTION NO. 3 BILL NO. 1 - EXTERNAL WORK |  |  |  | 0
SECTION NO. 4
BILL NO. 1
PROVISIONAL SUMS
WORK GROUP ALLOCATION
Unless otherwise stated, all items in this Bill will be allocated to External work
PREAMBLES
The General Preambles for Trades (2017 edition), as published by the Association of South African Quantity Surveyors, shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of items, fully described in the said General Preambles, will be entertained
The following "Supplementary Preambles" are incorporated in this bill to satisfy the requirements of the project and shall take precedence over the provisions of the said General Preambles
General
Work for which budgetary allowances are provided will be measured and valued in accordance with the JBCC principal building areement and its contract data (Edition 6,2 0f May 2018) and deducted in whole or in part if not required without any compensation for loss of profit on the said allowances
Profit
Where stated, the contractor may allow for profit if required
Subcontract Agreement
The item "attendance" which follows each provisional sum for nominated/selected subcontractors' work, shall be deemed to cover all the contractor's costs incurred in providing free of charge to the nominated/selected subcontractors the contractor's duties as described in clause 12.2 of the JBCC N/S Subcontractor Agreement
Special attendance on nominated/selected subcontractors
Where "special attendance" such as unloading, storing, placing in position, providing special power supplies, specific hoisting, cranage and scaffolding requirements, provision of temporary casing and/or other specific protection of the works, special security and clearing away rubbish is required, a separate item describing the specific requirements in detail is to be provided for the pricing of such requirements
Builder's work
Builder's work in connection with specialist services is given elsewhere in these bills of quantities
BUDGETARY ALLOWANCES
Wet Services, Plumbing, etc
1 | Allow and amount of R800,000.00 (Eight Hundred Thousand Rands Only) for wet services, plumbing and making good to walls,etc | Item | 1 |  | 0
Septic Tank
2 | Allow an amount of R750,000.00 (Seven Hundred and Fifty Thousand Rands Only) for a septic tank as per drawing GLDF_002_CIV_SEWER_08_R00 | Item | 1 |  | 0
Protection and Re-routing of services
3 | Allow and amount of R250,000.00 (Two Hundred and Fifty Thousand Rands Only) for protection and re-routing of services, etc | Item | 1 |  | 0
4 | Profit | Item | 1 |  | 0
5 | Attendance | Item | 1 |  | 0
| TOTAL SECTION NO. 4 BILL NO. 1 - PROVISIONAL SUMS |  |  |  | 0
SECTION NO. 5
CONTINGENCIES
1 | Allow R900 000.00 (Nine Hundred Thousand Rands Only) for the purposes of the contingencies. The contingencies to be used at the discretion of the client supported by the principal agent | Item | 1 |  | 0
| TOTAL SECTION NO. 5 BILL NO. 1 - CONTINGENCIES |  |  |  | 0
1 | Preliminaries and General |  |  |  | 0
2 | Sewer Works |  |  |  | 0
3 | External Works |  |  |  | 0
4 | Provisional Sums |  |  |  | 0
5 | Contingencies |  |  |  | 0
| Sub-total |  |  |  | 0
| Tax |  | 15% |  | 0
| Total |  |  |  | 0