## COVER AND ASSUMPTIONS
1. EXTENT OF CONTRACT & ASSUMPTIONS ON THE BOQ
Building contract
The work embodied in the contract comprises construction of a stable building with associated
services and external works.
The successful tenderer for this contract will be appointed in terms of the Principal Building
Agreement, July 2007 edition 5 prepared by the Joint Building Contracts Committee (JBCC
Series 2000) and amended by the quantity surveyor to suit the project.
Assumptions
- The bills of quantities have been produced without a civil, structural, mechanical & fire
engineer's input, all quantities & project specifications have been assumed and shall be
confirmed once these professionals are appointed and give accurate professional drawings.
- Ground conditions have been assumed to be adequate for the type of construction, no geotech
has been conducted. All costs for a geotech investigation shall be borne by the client.
- Contingency has been added at the final summary. This allowance shall be used on a proven
cost basis and signed off by the client and principal agent.
ACQUAINTANCE WITH TENDER DOCUMENTS
By submission of a tender, the contractor shall be deemed to have acquainted himself with the
contract documents, local requirements and laws and all aspects of the work envisaged in the
documents, prior to pricing and submission of a tender. It is of vital importance that the
tenderers visit the site prior to the submission of a tender to study conditions on site.
No claim resulting from failure to comply with any of the above will be entertained.
3. CONTRACT DOCUMENTS
The contract documents shall comprise:
* This tender enquiry document, bills of quantities and its annexures.
* All architectural drawings, to be read in conjunction with the bills of quantities:
4. BILLS OF QUANTITIES
These bills of quantities contain pages numbered consecutively as indicated in the Index.
Before the contractor submits his tender he should check the number of pages, and if any are
found to be missing or duplicated, or the figures or writing indistinct, or the tender documents
contain any obvious errors, he should apply to the quantity surveyors at once and have same
rectified as no liability whatsoever will be admitted by the quantity surveyors in respect of errors
in a tender due to the foregoing.
On no account should these documents be used for placing orders for materials. The contractor
may do so at his/ her own risk but shall not be reimbursed for additional costs incurred.
Unless a separate rate for the supply and for the installation of any items is specifically called
for, the supply and installation costs of any item shall be deemed to be fully included in the unit
price.
5. MATERIAL AND LABOUR COST FLUCTUATIONS
Tenders shall be fixed i.e. inclusive of provision for material and labour cost fluctuations during
the course of the works.
6. CONTRACT PERIOD
Building contract
Tenderers’ attention is drawn to the fact that no physical start & completion dates have been put
forward, it is required of the tenderers to propose a duration for this should the contract be
awarded to them.
7. CONDITIONS TO BE OBSERVED IN TENDERING
7.1 Tenders shall include Value Added Tax
7.2 The quantity surveyors will notify the tenderers of the tender results
7.3 The lowest, or any, or portion of any tender will not necessarily be accepted.
7.4 All tenders must be entered on the form provided herein.
7.5 Tenders must hold good for ninety (90) calendar days from the tender closing date as
stated herein.
7.6 All recipients of the tender document (whether they submit a tender or not) must treat
the details of the document as private and confidential
7.7 The employer will not be responsible for, or pay for, expenses or losses, which may be
incurred by any tenderer in the preparation of his tender.
8. TENDER INFORMATION
The employer may require additional information from the tenderer in order to evaluate the
tender. The tenderer is required to provide such information if so required by the employer.

## ROOIVAL FARM - PIGGERY
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
BILL No. 1
PRELIMINARIES
BUILDING AGREEMENT AND PRELIMINARIES
The JBCC Series 2000 Principal Building Agreement (July 2007 edition 5.0 - reprint 1) prepared by the Joint Building Contract Committee shall be the applicable building agreement, amended as hereinafter described
The JBCC Principal Building Agreement Contract Data EC and the JBCC Principal Building Agreement Contract Data CE form an integral part of this agreement
The ASSAQS Preliminaries (August 2010 edition) published by the Association of South African Quantity Surveyors for use with the said JBCC Principal Building Agreement shall be deemed to be incorporated in these bills of quantities
Contractors are referred to the abovementioned documents for the full intent and meaning of each clause thereof
These clauses are hereinafter referred to by clause number and heading only. Where standard clauses or alternatives are not entirely applicable to this agreement such modifications, corrections or supplements as will apply are given under each relevant clause heading and such modifications, corrections or supplements shall take precedence notwithstanding anything contrary contained in the abovementioned documents
Where any item is not relevant to this specific agreement such item is marked N/A, signifying "not applicable"
PREAMBLES FOR TRADES
The Model Preambles for Trades (2008 edition) as published by the Association of South African Quantity Surveyors shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of items fully described in the said Model Preambles will be entertained
Supplementary preambles are incorporated in these bills of quantities to satisfy the requirements of this project. Such supplementary preambles shall take precedence over the provisions of the said Model Preambles
The contractor's prices for all items throughout these bills of quantities must take account of and include for all of the obligations, requirements and specifications given in the said Model Preambles and in any supplementary preambles
PRICING OF PRELIMINARIES
Should the contractor select Option A in terms of sub clause 3.2.1 in the Contract Data - Contractor to Employer (CA) for the purpose of adjustment of these preliminaries, the amount entered into the amount column in these preliminaries is to be divided into one or more of the three categories provided namely Fixed (F), Value Related (V) and Time Related (T)
SECTION A - PRINCIPAL BUILDING AGREEMENT
Definitions
A | Clause 1.0 - DEFINITIONS AND INTERPRETATION | Item | 1
Clause 1.1 Definition of Bills of Quantities is amended by replacing the first sentence with the following:
BILLS OF QUANTITIES: The document drawn up in accordance with the Sixth Edition (Revised) of the Standard System of Measuring Builder's Work in South Africa issued by the Association of South African Quantity Surveyors, modified in certain respects where necessary to meet the requirements of certain particular cases. All adjustments arising out the Contract will be measured on the basis of these bills of quantities."
Clause 1.1 Definition of CPA is amended by replacing it with the following:
CPA: The JBCC Contract Price Adjustment Provisions used for the adjustment of the contract value.
Clause 1.1 Definition of interest is amended by replacing the first sentence with the following:
INTEREST: The bank rate that is applicable from time to time to registered banks when borrowing money from the Reserve Bank of the Republic of South Africa.
Clause 1.7 is amended by replacing it with the following:
For the purpose of sentence in relation to a payment certificate only, the parties consent to the jurisdiction of any court of the country in which district the site is located although the amount of the claim by either of the parties against the other may exceed the jurisdiction of such court
F:............................. V:............................ T:............................
Objective and preparations
A | Clause 2.0 - OFFER, ACCEPTANCE AND PERFORMANCE OBLIGATIONS | Item | 0
F:............................. V:............................ T:............................
B | Clause 3.0 - DOCUMENTS | Item | 0
Clause 3.6 is amended by replacing the last sentence with the following:
The original signed set of contract documents shall be held by the principal agent
F:............................. V:............................ T:............................
A | Clause 4.0 -DESIGN RESPONSIBILITY | Item | 0
The following new sub-clauses is hereby added to this clause:
4.4 Notwithstanding the provisions of 4.2, the Contractor shall ensure that every such nominated or selected subcontractor shall simultaneously with the signing of the relevant subcontract deliver to the Employer a Design Materials and Workmanship Warranty and Undertaking in favour of the Employer or, a Materials and Workmanship Undertaking strictly in accordance with the instructions or provisions contained in the tender documents for the nominated or selected subcontract works"
4.5 The Contractor shall be responsible for requesting from and/or clarifying of any design information with the Principal Agent timeously to avoid any delay in the intended date for Practical Completion"
F:............................. V:............................ T:............................
B | Clause 5.0 - EMPLOYER'S AGENTS | Item | 0
F:............................. V:............................ T:............................
A | Clause 6.0 - CONTRACTOR'S SITE REPRESENTATIVE | Item | 0
Clause 6.1 is amended by adding to the second sentence the following:
for the principal agent's approval, which approval shall not unreasonably withheld, but which approval may be withdrawn by notice at any time."
Clause 6.0 is amended by adding the following clause:
6.3 The contractor shall in addition keep on site, as necessary, competent senior foremen and sub foremen in charge of the work in progress. The principal agent may require details of past experience of such foremen to be submitted for approval by the principal agent before such foremen take up position on site."
Clause 6.0 is amended by adding the following clause:
6.4 The principal agent and the contractor shall provide one another with a list of names, addresses and telephone numbers of key personnel in their respective organisations who may be contacted in an emergency both during and outside office hours"
F:....................... V:..........................T:.............................
A | Clause 7.0 - COMPLIANCE WITH LAWS AND REGULATIONS | Item | 1
Without limiting the generality of the provisions of clause 7.0, the contractor's attention is drawn to the provisions of the Construction Regulations, 2003 issued in terms of the Occupational Health and Safety Act, 1993. It is specifically stated that the employer shall prepare a documented health and safety specification for the works. Refer to Annexure C for a copy of the relevant specification and that the employer shall ensure that the contractor has made provision for the cost of health and safety measures during the execution of the works. The contractor shall price opposite this item for compliance with the act and the regulations and the reasonable provisions of the aforementioned health and safety specifications
F:............................. V:............................ T:............................
B | Clause 8.0 - WORKS RISK | Item | 0
F:............................. V:............................ T:............................
C | Clause 9.0 - INDEMNITIES | Item | 0
F:............................. V:............................ T:............................
D | Clause 10.0 - GENERAL INSURANCES | Item | 0
The Contractor shall be registered with the Compensation Commissioner in accordance with the requirements of the Compensation for Occupational Injuries and Diseases Act No 130 of 1993, as amended and shall provide the Client with its COID registration number
F:........................... V:............................ T:...........................
E | Clause 11.0 - SPECIAL INSURANCES | Item | 0
F:............................. V:............................ T:...........................
A | Clause 12.0 - EFFECTING INSURANCES | Item | 0
F:............................ V:............................T:..........................
B | Clause 13.0 - ASSIGNMENT | Item | 0
F:............................. V:............................ T:............................
C | Clause 14.0 - SECURITY | Item | 0
Only a fixed construction guarantee will be accepted as security
F:............................ V:............................ T:............................
Execution
D | Clause 15.0 - PREPARATION FOR AND EXECUTION OF THE WORKS | Item | 0
The following should be added to Subclause 15.6.1
The contractor must submit with the tender a programme showing detailed information for the first 90 days of construction and an outline programme for the rest of the construction period of how the Works will be executed for consideration by the Principal Agent.
The programme will be finalized by mutual consent before signing of the contract
F:............................. V:....................... T:.............................
A | Clause 16.0 - SITE AND ACCESS | Item | 0
Clause 16.7 - Known services
Before removing existing services the contractor must inform the Employer who needs to give the approval to remove the services
Clause 16.8 - Protection of Trees
Protected trees will be indicated to the Contractor on a drawing
F:............................. V:............................ T:............................
B | Clause 17.0 - CONTRACT INSTRUCTIONS | Item | 0
F:............................. V:............................ T:............................
C | Clause 18.0 - SETTING OUT OF THE WORKS | Item | 0
F: ............................ V:...........................T:...........................
D | Clause 19.0 - TEMPORARY WORKS AND PLANT | Item | 0
Clause 19.1.1 is amended by adding the following:
The site must be adequately enclosed to ensure the safety of the residents. Area/s to be enclosed will be pointed out during the site inspection meeting."
F:............................. V:....................... T:.............................
E | Clause 20.0 - NOMINATED SUBCONTRACTORS | Item | 0
F:............................. V:............................ T:............................
F | Clause 21.0 - SELECTED SUBCONTRACTORS | Item | 0
F:............................. V:............................ T:............................
A | Clause 22.0 - EMPLOYER'S DIRECT CONTRACTORS | Item | 0
F:............................. V:............................ T:............................
B | Clause 23.0 -CONTRACTOR'S DOMESTIC SUBCONTRACTORS | Item | 0
F:............................. V:............................ T:............................
Completion
C | Clause 24.0 - PRACTICAL COMPLETION | Item | 0
The site will be handed over see Contract Data
The contractor must immediately start with the work after the site has been handed over subject to the contractor's site establishment and medical and safety inductions, which must be carried out before actual construction may commence
Practical completion will occur on see Contract Data
The following sub-clause is hereby added to this clause:
24.3.3 Practical Completion implies that the housing units are to be completed and operational and fit for occupation by the tenants.
The internal infrastructure and service installations including paving, landscaping, walkways, carports and the like will be completed, commissioned, operational and clean, and undisturbed access for occupants and their vehicles will be offered.
Any future work required shall be undertaken with minimal disruption to the occupants."
F:............................. V:............................ T:............................
A | Clause 25.0 - WORKS COMPLETION | Item | 0
Clause 25.1 is modified as follows:
"The employer intends that the works will be occupied by tenants upon practical completion. Before the principal agent may issue the certificate of practical completion, the contractor shall have brought the works to full completion in all respects and shall have corrected all defects that a reasonable inspection of the works would reveal. It is intended that the works completion list will have no outstanding works or defects that were apparent at the date of practical completion, but will only list defects that have been revealed after practical completion. Nevertheless, the employer reserves the right to waive this clause in respect of any section."
F:............................. V:............................ T:............................
B | Clause 26.0 - FINAL COMPLETION | Item | 0
F:............................. V:............................ T:............................
C | Clause 27.0 - LATENT DEFECTS LIABILITY PERIOD | Item | 0
F:............................. V:............................ T:............................
D | Clause 28.0 - SECTIONAL COMPLETION | Item | 0
F:............................. V:............................ T:............................
A | Clause 29.0 - REVISION OF DATE FOR PRACTICAL COMPLETION | Item | 0
Subclause 29.1.1 is hereby deleted and substituted with the following:
"Subclause 29.1.1
Exceptionally inclement weather, shall only relate to weather with a degree of inclemency which is materially greater than or is, materially beyond the average inclemency recorded in the past five years and/or recorded in terms of available records or otherwise for the site or, for the area in which the site is situated for the period/s in question. Any revision of the date of projected completion, which may in terms of this clause be allowed for exceptionally inclement weather, shall be related only to those periods of exceptionally inclement weather by which the average period of time, during which exceptionally inclement weather is experienced and/or recorded in the area in which the site is situated, is exceeded. The contractor is therefore to make allowances for normal vagaries of the weather"
The following shall be added to Subclause 29.3
"The removal and replacement of materials and/or workmanship which do not conform to specification or drawings shall not constitute grounds for the extension of the construction period nor for the adjustment of the contract value"
F:............................. V:............................ T:............................
B | Clause 30.0 - PENALTY FOR LATE OR NON-COMPLETION | Item | 0
F:............................. V:.......................... T:............................
Payment
A | Clause 31.0 - INTERIM PAYMENT | Item | 0
Sub clauses 31.5.3 and 31.8 are deemed to be deleted
Sub clause 31.6.5 is deemed to be deleted and replaced with:
Not withstanding this, or any other clause, materials and goods stored off site shall not be included in the amount authorised for payment
Subclause 31.9 is hereby amended by the substitution of "seven (7) calendar days" in the second line with "forty nine (49) calendar days".
F:............................. V:............................ T:............................
B | Clause 32.0 - ADJUSTMENT TO THE CONTRACT VALUE | Item | 0
Sub clauses 32.8 and 32.13 are deemed to be deleted
Add clause 32.16 as follows:
Where prices are submitted by the contractor or n/s subcontractor during the progress of the works in respect of contract instructions or in regard to a claim under the terms of the contract and notwithstanding the fact that such prices may be used in an interim payment certificate, there is to be no presumption of acceptance. Should the Principal Agent wish to accept any such prices prior to the issue of the final payment certificate, it shall be in writing
F:............................. V:............................ T:............................
C | Clause 33.0 - RECOVERY OF EXPENSE AND LOSS | Item | 0
F:............................. V:............................ T:............................
A | Clause 34.0 - FINAL ACCOUNT AND FINAL PAYMENT | Item | 0
Clause 34.3 is modified as follows:
"Should the contractor object to the final account with good reason, the contractor shall lodge with the principal agent full and comprehensive details of this objection in final form within fourteen (14) days of issuance of the final account failing which the
contractor strictly acknowledges that any such objection will have been waived by the contractor and shall be rejected by the principal agent ".
Clause 34.10 is modified as follows:
Delete the words "seven (7) calender days" and substitute with the words "twenty five (25) calender days".
F:............................. V:............................ T:............................
B | Clause 35.0 - PAYMENT TO OTHER PARTIES | Item | 0
F:............................. V:............................ T:............................
Termination
C | Clause 36.0 - TERMINATION BY EMPLOYER - CONTRACTOR'S DEFAULT | Item | 0
F:............................. V:............................ T:............................
D | Clause 37.0 - TERMINATION BY THE EMPLOYER - LOSS AND DAMAGE | Item | 0
F:............................. V:............................ T:............................
E | Clause 38.0 - TERMINATION BY THE CONTRACTOR - EMPLOYER'S DEFAULT | Item | 0
F:............................. V:............................ T:............................
A | Clause 39.0 - TERMINATION - CESSATION OF THE WORKS | Item | 0
F:............................. V:............................ T:............................
Dispute
B | Clause 40.0 - SETTLEMENT OF DISPUTES | Item | 0
F:............................. V:............................ T:............................
Contract agreement
C | Clause 41.0 - POST TENDER PROVISIONS | Item | 0
The required post tender information shall be inserted in the post tender provisions after consultation with the contractor
D | Clause 42.0 - CONTRACTUAL AGREEMENT | Item | 0
The required information of the contracting parties and the amount of the accepted contract sum shall be inserted in the contractual agreement for signature of the agreement by the contracting parties
CONTRACT DATA - EMPLOYER TO CONTRACTOR
Information necessary for elections and completion of those clauses contained in the Contract Data which are necessary for tender purposes is given hereunder. Where no information is given it shall mean that no specific requirements are expected
Tenderers are referred to the PRINCIPAL BUILDING AGREEMENT Contract Data EC for the full intent and meaning of the following clauses and are to provide for all costs and charges in connection therewith
1.0 - CONTRACTING AND OTHER PARTIES
1.1 Employer: Waterberg TVET College
Postnet Suite #59
Private X2449
Mokopane, 0600
Tel. No: 015 492 9000
Fax No: 015 492 9042
Physical Address:
Cnr Totius & Hooge Streets
Mokopane
0600
1.2Principal Agent: Komaru Consulting Engineer's
Postal Address: Office No. 12, 166 Protea Boulevard
Protea Glen Extension 12
Johannesburg, 1834
Tel. No: 084 787 7552
Fax No: N/A
E-mail: admin@komaru.co.za
1.3 Agent (1) Komaru Consulting Engineer's
Agent's Service: Architectural
Postal Address: Office No. 12, 166 Protea Boulevard
Protea Glen Extension 12
Johannesburg, 1834
Tel. No: 084 787 7552
Fax No: N/A
E-mail: admin@komaru.co.za
1.4 Agent (2) Komaru Consulting Engineer's
Agent's Service: Quantity Surveying
Postal Address: Office No. 12, 166 Protea Boulevard
Protea Glen Extension 12
Johannesburg, 1834
Tel. No: 084 787 7552
Fax No: N/A
E-mail: admin@komaru.co.za
1.5 Agent (3) Komaru Consulting Engineer's
Agent's Service Engineering - Civil and Structural
Postal Address: Office No. 12, 166 Protea Boulevard
Protea Glen Extension 12
Johannesburg, 1834
Tel. No: 084 787 7552
Fax No: N/A
E-mail: admin@komaru.co.za
1.6 Agent (3). Komaru Consulting Engineer's
Agent's Service Engineering - Electrical
Postal Address: Office No. 12, 166 Protea Boulevard
Protea Glen Extension 12
Johannesburg, 1834
Tel. No: 084 787 7552
Fax No: N/A
E-mail: admin@komaru.co.za
1.9 Interest of the principal agent or other agents in the project
NO
1.10 The principal agent named in 1.2 above is responsible for the preparation of the contract data schedule and must be contacted should the contractor be uncertain of the information provided or to be provided. Failure to complete the contract data schedule in full may result in the tender being disqualified
2.0 CONTRACT AND SITE INFORMATION
2.1 The law applicable to this agreement - South African
2.2 Works identification
The works comprises the construction of a school with alternative construction technology
2.3 Site description
The site is the existing Hani Park School Welkom
2.4 Possession of the site is to be given on
2.5 Period for commencement of the works after the contractor takes possession of the site
1 week
2.6 Completion of the works in sections is required
Yes
2.7 Waiver of the contractor's lien or right of continuing possession is required
Yes
2.8 Defined restrictions to the site area
Yes. Restrictions will be pointed out at the pre - tender site inspection.
2.9 Geotechnical investigation of the site has been undertaken
Not applicable
2.10 Existing premises will be occupied
Yes. Will be pointed at the pre - tender site inspection
2.11 Provision of temporary services required
Yes
2.11.1 Water Option A
Contractor to provide labour and material for pipe work, meter, connections, etc. The clause regarding standing time will be disregarded
2.11.2 Electricity Option A
Contractor to provide labour and material for cables, trenches, meter, connections, etc.
The clause regarding standing time will be disregarded
2.11.3 Telecom Option A
2.11.4 Ablutions Option A
2.12 Protection of existing trees
Yes
3.0 INSURANCES AND SECURITIES
3.1 Contract works insurance to be effected by Contractor
For the sum of: Contract Sum plus 30%
With a deductable of: Nil
3.2 Supplementary/Special Insurances effected by contractor
For the sum of the Contract Sum plus 30%
With a deductable of: Nil
3.3 Public liability insurance to be effected by Contractor
For the Sum of R 5 000 000.00 (Five Million Rand) per claim
With a deductable of: Nil
3.4 Support insurance to be effected by the employer
Not Applicable
3.5 Special insurance to be effected by
Not applicable
4.0 PRACTICAL COMPLETION DATES AND PENALTIES
4.1 The dates for practical completion for each block is as follows:
The penalty per calendar day is
5.0 DOCUMENTS AND GENERAL
5.1 Construction document copies to be supplied to the Contractor free of charge
Two
5.2 The priced document may be used as a specification of materials and goods and work methods
No
5.3 The Contractor shall provide a schedule of rates
No
5.4 Changes made to JBCC standard documents
Yes
5.5 On acceptance of the tender the priced document is to be submitted within the stated working days
At time of tender
5.6 Work to be undertaken by direct contractors
Yes
5.7 On achievement of practical completion the contractor is to hand over manuals etc related to the works listed below
Electrical, Plumbing, Fire and any other installations as may be required
5.8 Interim payment certificate to be issued by
25th day of every month
6.0 CHANGES MADE TO THE STANDARD DOCUMENT
Principal Building Agreement
Clause 1 amended
Clause 3 amended
Sub-Clause 4.4 added
Clause 6 amended
Clause 7 amended
Clause 10 amended
Clause 15 amended
Clause 16 amended
Clause 19 amended
Clause 24 amended
Cause 25 amended
Clause 29 amended
Clause 31 amended
Clause 32 amended
Clause 34 amended
Preliminaries
Clause 2.1 amended
Clause 2.2 amended
Clause 2.3 amended
Clause 4.2 amended
Clause 6.2 amended
Clause 9.4 amended
7.0 DECLARATION BY THE PRINCIPAL AGENT
I, the principal agent named in 1.2 above, declare that the information provided above is complete and accurate at the time of calling for tenders. Where necessary, should any of the above information need to be varied, tenderers will be forthwith informed thereof in writing
-----------------------------------------
Principal Agent
-----------------------------------------
Date
CONTRACT DATA - CONTRACTOR TO EMPLOYER
The following information must be completed in full by the Tenderer and must be submitted with the tender
The option not chosen must be crossed out
The Tenderer is referred to the PRINCIPAL BUILDING AGREEMENT Contract Data CE for the full intent and meaning of the following clauses and to provide for all costs and charges in connection therewith
A | 1.0 CONTRACTING PARTY | Item | 0
1.1 Contractor ...........................................................................
Postal Address ...........................................................................
Code ..............
Tel ......................................................
Fax ....................................................
e-mail .................................................
Tax / Vat Registration No ......................................
1.2 Physical Address ............................................................................
Tel ......................................................
Fax ....................................................
e-mail .................................................
2.0 SECURITIES
2.1 The security provisions selected are:
2.1.1 Variable Construction Guarantee Yes / No
2.1.2 Fixed Construction Guarantee and
Payment Reduction Yes / No
2.1.3 Advance Payment is required Yes / No
Amount ____________________________
2.1.4 Advance Payment Guarantee to be
provided Yes / No
3.0 PAYMENT AND ADJUSTMENT OF PRELIMINARIES
3.1 Payment of preliminaries
3.1.1 Option A
3.1.2 Option B
3.2 Adjustment of preliminaries
3.2.1 Option A
3.2.2 Option B
3.2.3 Payment certificate cash flow
3.2.4 The contract value shall be adjusted according CPAP NO
3.2.5 Payment of preliminaries Option A / Option B
3.26 Adjustment of preliminaries Option A / Option B
4.0 EMPLOYER CHANGES TO JBCC STANDARD DOCUMENTS
4.1 Changes in terms of the Employer's Contract Data are accepted Yes / No
SECTION B - PRELIMINARIES
DEFINITIONS AND INTERPRETATIONS
A | Clause 1.0 - DEFINITIONS AND INTERPRETATIONS | Item | 0
F:............................. V:............................ T:............................
DOCUMENTS
A | Clause 2.1 - Checking of documents | Item | 0
The items in these provisional bills of quantities are to be read and priced in conjunction with and the descriptions regarded as amplified by the Model Preambles for Trades as recommended and published by the Association of South African Quantity Surveyors, 2008 edition, and no claim arising from brevity of description of items fully described in the said Model Preambles for Trades will be entertained.
F:............................. V:............................ T:............................
B | Clause 2.2 - Provisional bills of quantities | Item | 0
The following shall be added to clause 2.2
These bills of quantities shall not be used for ordering purposes
F:............................. V:............................ T:............................
C | Clause 2.3 - Availability of construction documentation | Item | 0
The budgetary allowances and selected subcontract amounts allocated for subsequent trades included in this document will be separately procured, based on multiple procurement of selected subcontractors during the construction period
F:............................. V:............................ T:............................
PREVIOUS WORK AND ADJOINING PROPERTIES
D | Clause 3.1 - Previous work - dimensional accuracy | Item | 0
F:............................. V:............................ T:............................
E | Clause 3.2 - Previous work - defects | Item | 0
F:............................. V:............................ T:............................
A | Clause 3.3 - Inspection of adjoining properties | Item | 0
F:............................. V:............................ T:............................
SAMPLES, SHOP DRAWINGS AND MANUFACTURER'S INSTRUCTIONS
B | Clause 4.1 - Samples of materials | Item | 0
F:............................. V:............................ T:............................
C | Clause 4.2 - Workmanship samples | Item | 0
Add the following paragraph:
Construction must be carried out to the following maximum tolerances:
Levelness of horizontal surfaces maximum 10mm deviation over 2 metres
Plumbness of vertical surfaces maximum 10mm deviation over 2 metres including out of squareness of corners or openings"
F:............................. V:............................ T:............................
D | Clause 4.3 - Shop drawings | Item | 0
F:............................. V:............................ T:............................
E | Clause 4.4 - Compliance with manufacturer's instructions | Item | 0
F:............................. V:............................ T:............................
DEPOSITS AND FEES
F | Clause 5.1 - Deposits and fees | Item | 0
F:............................. V:............................ T:............................
TEMPORARY SERVICES
A | Clause 6.1 - Water | Item | 0
F:.......................... V:....................... T:..............................
B | Clause 6.2 - Electricity | Item | 0
The following shall be added to clause 6.2
No delay claims will be accepted by the Employer in terms of any power outages by the electricity supply agency"
F:..................................... V:............................
T:.....................................
C | Clause 6.3 - Telecommunication facilities | Item | 1
F:............................. V:............................
T:..............................
D | Clause 6.4 - Ablution facilities | Item | 0
F:................................... V:............................
T:...................................
PRIME COST AMOUNTS
E | Clause 7.1 - Responsibility for prime cost amounts | Item | 0
F:............................. V:............................ T:............................
SPECIAL ATTENDANCE ON N/S SUBCONTRACTORS
F | Clause 8.1 - Special attendance | Item | 0
F:............................. V:............................ T:............................
GENERAL
G | Clause 9.1 - Protection of the works | Item | 0
F:............................. V:............................ T:............................
A | Clause 9.2 - Protection/isolation of existing/sectionally occupied works | Item | 1
F:............................. V:............................ T:............................
B | Clause 9.3 - Security of the works | Item | 1
F:................................... V:............................
T:...................................
C | Clause 9.4 - Notice before covering work | Item | 0
Add the following paragraphs:
The Contractor will notify the Principal Agent after completion of the following and before starting the next operation:
Foundation excavation before casting footings
After casting of footings before building foundation brickwork
After building of brickwork before plastering
After plastering before tiling or painting
Failure by the Contractor to notify the Principal Agent timeously may incur additional cost for rectification which cost will be for the account of the Contractor.
The Contractor must take inspection periods into account when the programme for the project is compiled
F:............................. V:............................ T:............................
D | Clause 9.5 - Disturbance | Item | 0
F:............................. V:............................ T:............................
A | Clause 9.6 - Environmental disturbance | Item | 0
F:............................. V:............................ T: .........................
N/A
B | Clause 9.7 - Works cleaning and clearing | Item | 0
F:............................... V:............................
T:...............................
C | Clause 9.8 - Vermin | Item | 0
F:............................. V:............................ T:............................
D | Clause 9.9 - Overhand work | Item | 0
F:............................. V:............................ T:............................
SECTION C - SPECIFIC PRELIMINARIES
E | Labour record. | Item | 0
At the end of each month the contractor shall provide the principal agent and the employer with a written record, in schedule form, reflecting the number and description of tradesmen and labourers employed by him and all subcontractors on the works each day. The record shall show the name and surname of the tradesperson or labourer, ID number, permanent address of person and hours worked
F | Plant record. | Item | 0
At the end of each month the contractor shall provide the principal agent and the employer with a written record, in schedule form, reflecting the number, type and capacity of all plant and hand tools, currently used on the works. The record must also show the date the plant was inspected and who carried out the inspection
A | Site instructions | Item | 0
Contract Instructions issued on site are to be recorded in triplicate in a site instruction book which is to be maintained on site by the contractor
F:............................. V:............................ T:............................
B | Warranties for material and workmanship | Item | 0
Where warranties for materials and/or workmanship are called for, the contractor shall obtain a written warranty, addressed to the employer, from the firm supplying the materials and/or doing the work and shall deliver same to the principal agent on the final completion of the contract. The warranty shall state that workmanship, materials and installation are warranteed for a specified period from the date of final completion and that any defects that may arise during the specified period shall be made good at the expense of the firm supplying the materials and/or doing the work, upon written notice to do so. The warranty will not be enforced if the work is damaged by defects in the construction of the building in which case the responsibility for replacement shall rest entirely with the contractor
F:.......................V:.........................T:............................
C | Co-operation of contractor for cost management | Item | 0
It is specifically agreed that the contractor accepts the obligation of assisting the principal agent in implementing proper cost management. The contractor will be advised by the principal agent of all cost management procedures which will be implemented to ensure that the final building cost does not exceed the budget. The principal agent undertakes to make available to the contractor all budgetary allowances and cost assessments/reports to enable the proper procedure to be implemented and the contractor shall attend all cost plan review and cost management meetings. The contractor undertakes to extend these procedures, as necessary, to all subcontractors
F:...........................V:.........................T:.........................
A | Propping of floors below | Item | 0
The contractor is advised that propping of floors below may be required if he wishes to use any areas of completed suspended reinforced concrete slabs for vehicle access, storage of materials and goods and location of plant, scaffolding, etc. The location of these areas and any necessary propping shall be approved by the principal agent and the cost thereof shall be borne by the contractor
F:......................... V:........................... T:..........................
B | Use of lifts and or temporary hoists | Item | 0
The contractor shall devise his/her own temporary access for equipment into the building and the removal of rubble from the building.
If the contractor makes use of a hoist and/or scaffolding and creates temporary openings in order to gain access, or for any other reason, the contractor shall upon completion of the Works reinstate all affected existing work to match its original condition.
Strict safety rules shall apply to the use of any scaffolding, hoists or lifts.
C | Copyright | Item | 0
The ownership of the copyright in and to all drawings, specifications, models and documents of any nature, delivered to the Contractor, or produced by, or on behalf of the Contractor in connection with the works, shall remain vested in, and/or is hereby assigned to, the Employer by the Contractor
F...........................V...............................T..........................
A | Confidentiality | Item | 0
The Contractor shall treat all drawings, specifications, models and documents of any nature delivered to the Contractor, or produced by, or on behalf of the Contractor in connection with the works as being confidential. The Contractor shall not copy, photograph and/or repeat either wholly, or in part, any of the contract documents referred to above (except insofar as may be necessary in connection with the project). The Contractor shall return to the Principal Agent with his tender, all contract documents issued herewith, and, upon completion of the Works deliver to the Principal Agent all contract documents of any nature pertaining to the project
F.................................V......................T.............................
B | Testing of windows for watertightness | Item | 0
Each window shall be tested for watertightness with water sprayed on using adequate pressure. If in the opinion of the principal agent, the pressure proves to be inadequate, then the pressure shall be boosted by means of compressed air or other approved means
F:....................... V:......................... T:.........................
C | Testing of flat roof waterproofing for watertightness | Item | 0
Flat roof waterproof areas shall be prepared with small sand dykes around them of a size and enclosing an area approved by the principal agent, flooded with water and kept "ponded" for at least 36 hours as a test to ensure the watertightness of the waterproofing and before any further construction work is carried out above the waterproofing
F:....................... V:........................... T:............................
SUMMARY OF CATEGORIES
Category : Fixed
Category : Value
Category : Time
CARRIED TO FINAL SUMMARY
BILL NO. 1
DEMOLITIONS
User note
Insert preambles/specifications as may be required or in order to supplement any applicable preambles, specifications or bills of quantities descriptions
Take note that these Model Bills of Quantities utilise abbreviated descriptions
The Model Preambles for Trades 2008 published by the Association of South African Quantity Surveyors is designed to support and extend the abbreviated bills of quantities descriptions by inter alia referring to SANS construction standards. Where such model preambles are not applicable (eg where BS or Euro construction standards are applicable or the design consultants provide other preambles/specifications for insertion), users are to ensure that the abbreviated descriptions when read in conjunction with the applicable measuring system, represents the full description by extending the abbreviated bills of quantities descriptions and/or by inserting appropriate preambles or specifications
Consider inserting the preambles hereunder when using the abovementioned Model Preambles for Trades 2008
View site
Before submitting his tender the tenderer shall visit the site and satisfy himself as to the nature and extent of the work to be done and the value of the materials contained in the buildings or portions of the buildings to be demolished. No claim for any variations of the contract sum in respect of the nature and extent of the work or of inferior or damaged materials will be entertained
Explosives
No explosives whatsoever may be used for demolition purposes unless otherwise stated
General
Water supply pipes and other piping in ground that may be encountered and found necessary to disconnect or cut, shall be effectually stopped off or grubbed up and removed, and any new connections that may be necessary shall be made with proper fittings to the satisfaction of the principal agent
Unless otherwise described all materials are to become the property of the contractor and are to be removed from the site
Taking out/off and removing sundry metalwork
| Steel Compartments "grower and feed rooms' 1000mm high from concrete floor, including making good concrete finish | m | 88
| Steel Compartments "bore and saw room' 1000mm high from concrete floor, including making good concrete finish | m | 34
Steel Ferrowing Cage " Ferrowroom'' 1000mm high from concrete floor, including making good concrete finish
| Steel Dry saw crate 650x2000x1000mm high made of 50mm diameter galvanised steel from concrete floor, including making good concrete finish | m | 28
| 0,65mm Carrogated steel roof sheeting on the side of the structure | m | 108
CARRIED TO FINAL SUMMARY
BILL NO 3
CONCRETE, FORMWORK AND REINFORCEMENT
User note
Insert preambles/specifications as may be required or in order to supplement any applicable preambles, specifications or bills of quantities descriptions
Take note that these Model Bills of Quantities utilise abbreviated descriptions
The Model Preambles for Trades 2008 published by the Association of South African Quantity Surveyors is designed to support and extend the abbreviated bills of quantities descriptions by inter alia referring to SANS construction standards. Where such model preambles are not applicable (eg where BS or Euro construction standards are applicable or the design consultants provide other preambles/specifications for insertion), users are to ensure that the abbreviated descriptions when read in conjunction with the applicable measuring system, represents the full description by extending the abbreviated bills of quantities descriptions and/or by inserting appropriate preambles or specifications
Consider inserting the preambles hereunder when using the abovementioned Model Preambles for Trades 2008
Cost of tests
The costs of making, storing and testing of concrete test cubes as required under clause 7 "Tests" of SABS 1200 G shall include the cost of providing cube moulds necessary for the purpose, for testing costs and for submitting reports on the tests for approval. The testing shall be undertaken by an approved independent firm or institution nominated by the contractor (test cubes are measured separately)
Breeze concrete
Breeze concrete shall consist of twelve parts clean dry furnace ash, free from coal or other foreign matter, to one part cement (1:12); the ash graded up to particles which will pass a 16,5mm ring from a minimum which fails to pass a 4,75mm mesh. The finer materials from the screening are to be first mixed with the cement into a mortar and the ash added afterwards and thoroughly incorporated
Lightweight concrete
Lightweight concrete shall have a density of 600kg/m3 for the top 50mm and 400kg/m3 for the remaining thickness. The minimum thickness at outlets, channels, etc shall be 50mm
Formwork
Descriptions of formwork shall be deemed to include use and waste only (except where described as "left in" or "permanent"), for fitting together in the required forms, wedging, plumbing and fixing to true angles and surfaces as necessary to ensure easy release during stripping and for reconditioning as necessary before re-use
The vertical strutting shall be carried down to such construction as is sufficiently strong to afford the required support without damage and shall remain in position until the newly constructed work is able to support itself
Formwork to soffits of solid slabs etc shall be deemed to be to slabs not exceeding 250mm thick unless otherwise described
Formwork to soffits of slabs, beams, etc shall be deemed to be propped up exceeding 1,5m and not exceeding 3,5m high unless otherwise described
Formwork to sides of bases, pile caps, ground beams, etc will only be measured where it is prescribed by the engineer for design reasons. Formwork necessitated by irregularity or collapse of excavated faces will not be measured and the cost thereof shall be deemed to be included in the allowance for taking the risk of collapse of the sides of the excavations, provision for which is made in "Earthworks"
UNREINFORCED CONCRETE CAST AGAINST EXCAVATED SURFACES
10MPa/15mm concrete
| 50mm Surface blinding under surface beds including chipping the existing floor for better settlement of the new floor | m3 | 15
CARRIED TO FINAL SUMMARY
BILL NO 4
MASONRY
User note
Insert preambles/specifications as may be required or in order to supplement any applicable preambles, specifications or bills of quantities descriptions
Take note that these Model Bills of Quantities utilise abbreviated descriptions
The Model Preambles for Trades 2008 published by the Association of South African Quantity Surveyors is designed to support and extend the abbreviated bills of quantities descriptions by inter alia referring to SANS construction standards. Where such model preambles are not applicable (eg where BS or Euro construction standards are applicable or the design consultants provide other preambles/specifications for insertion), users are to ensure that the abbreviated descriptions when read in conjunction with the applicable measuring system, represents the full description by extending the abbreviated bills of quantities descriptions and/or by inserting appropriate preambles or specifications
Consider inserting the preambles hereunder when using the abovementioned Model Preambles for Trades 2008
BRICKWORK
Sizes in descriptions
Where sizes in descriptions are given in brick units, "one brick" shall represent the length and "half brick" the width of a brick
User note
The following preamble generally applies for works in hot and humid coastal areas
Bagged and sealed walls
Walls in two skins described as "bagged and sealed" shall be deemed to include having the outer face of the inner skin bagged with 1:6 cement and sand mixture and sealed with two coats bitumen emulsion waterproofing coating
Face bricks
Bricks shall be ordered timeously to obtain uniformity in size and colour
Pointing
Descriptions of recessed pointing to fair face brickwork and face brickwork shall be deemed to include square recessed, hollow recessed, weathered pointing, etc
BLOCKWORK
Concrete masonry units
Blocks are to be either solid or hollow modular dense concrete masonry units having a compressive strength of 7MPa
Wall ties for blockwork
Wall ties shall be polypropylene ties complying with BS 76377. Ties for hollow walls shall be of sufficient length to allow not less than 75mm of each end to be built into the blockwork. Ties are to be spaced at intervals of not more than 1m in the horizontal direction and not more than 400mm staggered in the vertical direction except at openings, vertical joints or ends of walls where they are to be placed vertically above each other
Blockwork
Blockwork shall comply with SANS 10145 "Concrete Masonry Construction"
Surfaces to be plastered shall have joints raked out to a depth of at least 10mm to provide a key. Cavities of hollow walls shall be kept free of mortar droppings or other undesirable matter. Every second perpend of the bottom course of the external skin of hollow walls shall be left open as a weep hole
Standard complementary blocks
Descriptions of blockwork shall be deemed to include standard complementary blocks such as corner, three-quarter, half and quarter blocks required in the construction of corners, reveals, jambs, ends, etc to solid and hollow walls and for bonding as necessary
DECORATIVE BLOCKS
Blocks shall be of approved manufacture, sound, well burnt or cured and uniform and true in size, shape and colour
SUPERSTRUCTURE
Brickwork of NFP bricks in class II mortar
| Half brick walls | m2 | 108
BRICKWORK SUNDRIES
2,5mm Galvanised brick reinforcement
| 75mm Wide reinforcement built in horizontally | m | 216
CARRIED TO FINAL SUMMARY
BILL NO 5
WATERPROOFING
User note
Insert preambles/specifications as may be required or in order to supplement any applicable preambles, specifications or bills of quantities descriptions
Take note that these Model Bills of Quantities utilise abbreviated descriptions
The Model Preambles for Trades 2008 published by the Association of South African Quantity Surveyors is designed to support and extend the abbreviated bills of quantities descriptions by inter alia referring to SANS construction standards. Where such model preambles are not applicable (eg where BS or Euro construction standards are applicable or the design consultants provide other preambles/specifications for insertion), users are to ensure that the abbreviated descriptions when read in conjunction with the applicable measuring system, represents the full description by extending the abbreviated bills of quantities descriptions and/or by inserting appropriate preambles or specifications
Consider inserting the preambles hereunder when using the abovementioned Model Preambles for Trades 2008
Waterproofing
Waterproofing of roofs, basements, etc shall be laid under a ten year guarantee. Waterproofing to roofs shall be laid to even falls to outlets etc with necessary ridges, hips and valleys. Descriptions of sheet or membrane waterproofing shall be deemed to include additional labour to turn-ups and turn-downs
DAMPPROOFING OF WALLS AND FLOORS
User note
Where SANS 952-1985 in the following headings is not applicable, refer to other suitable construction standards or provide full specifications
One layer type FV dampproof course
One layer 375 micron embossed polyethylene dampproof course (SANS 952-1985 type B)
| In walls | m2 | 108
CARRIED TO FINAL SUMMARY
BILL NO 6
FLOOR COVERINGS, WALL LININGS, ETC
User note
Insert preambles/specifications as may be required or in order to supplement any applicable preambles, specifications or bills of quantities descriptions
Take note that these Model Bills of Quantities utilise abbreviated descriptions
The Model Preambles for Trades 2008 published by the Association of South African Quantity Surveyors is designed to support and extend the abbreviated bills of quantities descriptions by inter alia referring to SANS construction standards. Where such model preambles are not applicable (eg where BS or Euro construction standards are applicable or the design consultants provide other preambles/specifications for insertion), users are to ensure that the abbreviated descriptions when read in conjunction with the applicable measuring system, represents the full description by extending the abbreviated bills of quantities descriptions and/or by inserting appropriate preambles or specifications
Consider inserting the preambles hereunder when using the abovementioned Model Preambles for Trades 2008
Fixing
Floor coverings, wall linings, etc shall, where applicable, be fixed with adhesive as recommended by the manufacturers of the flooring, linings, etc
FLOOR COVERINGS
| Concrete slats 1.2 mtr x 0.45 mtr including delivery | m2 | 269
CARRIED TO FINAL SUMMARY
BILL NO 7
IRONMONGERY
User note
Insert preambles/specifications as may be required or in order to supplement any applicable preambles, specifications or bills of quantities descriptions
Take note that these Model Bills of Quantities utilise abbreviated descriptions
The Model Preambles for Trades 2008 published by the Association of South African Quantity Surveyors is designed to support and extend the abbreviated bills of quantities descriptions by inter alia referring to SANS construction standards. Where such model preambles are not applicable (eg where BS or Euro construction standards are applicable or the design consultants provide other preambles/specifications for insertion), users are to ensure that the abbreviated descriptions when read in conjunction with the applicable measuring system, represents the full description by extending the abbreviated bills of quantities descriptions and/or by inserting appropriate preambles or specifications
Consider inserting the preambles hereunder when using the abovementioned Model Preambles for Trades 2008
Proprietary items
Where applicable the manufacturers' names or product catalogue titles are given in sub-headings preceding the items Prices are to be based on the specific products/articles specified. If tenderers wish to offer alternative products/articles for certain items, these items are to be clearly marked and the alternative specification given with supporting brochures etc clarifying the features of the products/articles offered On request returnable samples are to be provided to the principal agent for consideration
LOCKS
Keys
Unless otherwise described locks shall have two keys each
EN-SUITE LOCKS
The following locks are to be suitable for master key operation
The following locks are to be suitable for master and grand master key operation
Manufactured by Union
In accordance with catalogue
| 3 Lever ockset. | No | 2
CARRIED TO FINAL SUMMARY
BILL NO 8
METALWORK
User note
Insert preambles/specifications as may be required or in order to supplement any applicable preambles, specifications or bills of quantities descriptions
Take note that these Model Bills of Quantities utilise abbreviated descriptions
The Model Preambles for Trades 2008 published by the Association of South African Quantity Surveyors is designed to support and extend the abbreviated bills of quantities descriptions by inter alia referring to SANS construction standards. Where such model preambles are not applicable (eg where BS or Euro construction standards are applicable or the design consultants provide other preambles/specifications for insertion), users are to ensure that the abbreviated descriptions when read in conjunction with the applicable measuring system, represents the full description by extending the abbreviated bills of quantities descriptions and/or by inserting appropriate preambles or specifications
Consider inserting the preambles hereunder when using the abovementioned Model Preambles for Trades 2008
Descriptions of bolts, anchors, etc
Descriptions of bolts shall be deemed to include nuts and washers
Descriptions of expansion anchors and bolts and chemical anchors and bolts shall be deemed to include nuts, washers and mortices in brickwork or concrete
Items described as "holed for bolt(s)" shall be deemed to exclude the bolts unless otherwise described
Items described as "plugged" shall be deemed to include screwing to fibre, plastic or metal plugs at not exceeding 600mm centres
Aluminium doors, windows, etc
Doors and windows shall comply with AAAMSA design criteria Glazing shall comply with SAGGA regulations. Glass shall be type ? laminated performance glass as shown on the window schedules/drawings appended to these bills of quantities (as described in the headings to window descriptions?). Glass thickness shall comply with SAGGA regulations irrespective of thicknesses shown on the schedules/drawings Doors and windows shall be supplied with protective tape and plastic and shall be removed only once surrounding trades have been completed For purpose made windows and doors, refer to drawings annexed to (issued separately with?) these bills of quantities
The following certificates shall be provided prior to commencement of site work:1 A copy of the relevant AAAMSA Performance Test Certificate from the manufacturer/contractor supplying the architectural aluminium product 2 A Certificate of Conformance confirming that anodising or powder coating has been processed in accordance with SANS 999 and SANS 1796 respectively
3 A powder guarantee of not less than 15 years issued by the powder manufacturer. The specific conditions contained in this guarantee shall form part of the powder coating process 4 A Certificate of Conformance confirming that glazing has been installed in accordance with SANS 0137, ensuring that safety glazing materials have been installed in the mandatory areas and that each individual pane of safety glazing materials has been permanently marked5 A warranty from the manufacturer of the laminated safety glass and/or hermetically sealed glazing units guaranteeing the products against delamination and colour degredation for a period of not less than five years
STEEL GATES, SCREENS, ETC
GALVANISED STEEL GATES, SCREENS, ETC
Welded screens and gates to Weaners and Grower pen
| Plastic penning 750mm high (500mm x 35 wide board ) with 2 Galv. Bars | m | 65
Welded screens and gates to Bore and Ferrowing pen
| Plastic penning 750mm high (500mm x 35 wide board ) with 2 Galv. Bars | m | 49
FERROWING CRATE
| Farrowing Pens 2.4 x 1.8m cpl. with crates - tiltable trough, cast iron slat below sow, plastic flooring on either side of cast iron, fibre beam supports, plastic penning(500mm high with galvanised posts), drinking manifold for sows and piglets including nipples, infra-red heater 175kW and feed pan for suckling | No | 4
DRY SAW ROOMS
| Dry sow crates 2.2mtrs x 0.650mtrs with bars on top – galvanised steel | No | 16
| Slurry tier and connecting plug | No | 20
| Manual curtain with 12mtrs x 1.5mtrs with manual operation | No | 4
GALVANISED PRESSED STEEL COMBINATION DOORS AND FRAMES
| Door 813 x 2083 mm high with rebated frame suitable for half brick wall and with Union mortice lock | No | 2
CARRIED TO FINAL SUMMARY
BILL NO 9
PROVISIONAL SUMS
User note
Insert preambles/specifications as may be required or in order to supplement any applicable preambles, specifications or bills of quantities descriptions
Take note that these Model Bills of Quantities utilise abbreviated descriptions
The Model Preambles for Trades 2008 published by the Association of South African Quantity Surveyors is designed to support and extend the abbreviated bills of quantities descriptions by inter alia referring to SANS construction standards. Where such model preambles are not applicable (eg where BS or Euro construction standards are applicable or the design consultants provide other preambles/specifications for insertion), users are to ensure that the abbreviated descriptions when read in conjunction with the applicable measuring system, represents the full description by extending the abbreviated bills of quantities descriptions and/or by inserting appropriate preambles or specifications
General
Work for which budgetary allowances are provided will be measured and valued in accordance with the relevant ?building agreement? ?building contract? and deducted in whole or in part if not required without any compensation for loss of profit on the said allowances
Prime cost amounts and provisional sums are net. Prime cost amounts shall include for delivery to site of all articles concerned Provisional sums are for material and equipment supplied and installed complete by firms of specialists
Profit
Where stated, the contractor may allow for profit if required
User note
Refer hereunder to "nominated subcontractors" or "selected subcontractors" or both as the case may be and in accordance with the relevant building agreement (building contract) Where "attendance" is defined in the relevant subcontract agreement/subcontract, the user is to refer thereto and is to ensure that the designations therein are used. Where "attendance" is not defined in the relevant subcontract agreement/subcontract, the user is to provide a detailed description of the "attendance" required from the contractor
General attendance on nominated/selected subcontractors
User note
Use the following descriptions where the JBCC N/S Subcontract Agreement is applicable
The item "attendance" which follows each provisional sum for nominated/selected subcontractors' work, shall be deemed to cover all the contractor's costs incurred in providing free of charge to the nominated/selected subcontractors the contractor's duties as described in clause 12.2 of the JBCC N/S Subcontract Agreement
Special attendance on nominated/selected subcontractors
Where "special attendance" such as unloading, storing, placing in position, providing special power supplies, specific hoisting, cranage and scaffolding requirements, provision of temporary casing and/or other specific protection of the works, special security and clearing away rubbish is required, a separate item describing the specific requirements in detail is to be provided for the pricing of such requirements
Builder's work
Builder's work in connection with specialist services is given elsewhere in these bills of quantities
PROVISIONAL SUMS FOR NOMINATED/SELECTED SUBCONTRACT WORKS
Electrical And Water
| Provide the sum of R20 000,00 (Twenty Thousand Rands) for fixing water and electical reticulation | Item | 1
| Provide the sum of R5000,00 (Five Thousand Rands) for fixing the sides to create 2 windows | Item | 1
| Provide the sum of R6 000,00 (six Thousand Rands) for removal and replacement of a 1.1kv Water pump | Item | 1
| Provide the sum of R20 000,00 (Twenty Thousand Rands) for unforeseen work | Item | 1
CARRIED TO FINAL SUMMARY
FINAL SUMMARY
1 | PRELIMINARIES
2 | DEMOLITIONS
3 | CONCRETE, FORMWORK AND REINFORCEMENT
4 | MASONRY
5 | WATERPROOFING
6 | FLOOR COVERINGS, WALL LININGS, ETC
7 | IRONMONGERY
8 | METALWORK
9 | PROVISIONAL SUMS
Sub Total
3 | CONTINGENCY ALLOWANCE@ 5%
Sub Total
Vat @ 15%
CARRIED TO FORM OF TENDER